## Consolidated Defect Register
AXIORA PULSE — CONSOLIDATED CROSS-STAGE DEFECT REGISTER
Master register of defects across all evaluated development stages (Stage 02 through Stage 10)
Defect ID | Stage ID | Stage Name | Module / Area | Capability Reference | Defect Title | Defect Category | Severity | Priority | Preconditions | Reproduction Steps | Expected Result | Actual Result | Evidence Reference | Affected Downstream Stages | Recommended Remediation | Retest Status
S02-DEF-001 | Stage_02 | Market Research & Business Model | Survey Intelligence UI | SIA.1 | Survey Intelligence Screen Displays Un-actionable Empty State Without Creation CTA | UI / Workflow | High | P2 | Workspace in GATHERING_INFO or READY_TO_VALIDATE state | Navigate to /workspace/:id/survey | Survey tab should display educational CTA explaining that survey will be generated upon idea validation, or provide manual survey builder. | Displays plain message 'No surveys found' with no actionable button, explanation, or link back to chat. | S02-EV-004_Survey_Intelligence_Empty_State.png | Stages 3-10 | Add an empty-state card with 'Validate Idea First' button that navigates back to the mentor chat. | Open
S02-DEF-002 | Stage_02 | Market Research & Business Model | Workspace Navigation | GTM.4, GTM.5 | Missing Dedicated UI Screens for Business Model, Pricing, and Competitor Dynamics | Product / Architecture | Medium | P3 | Workspace active in QA | Review workspace navigation tabs | Documented Stage 2 scope includes Business Model, Unit Economics, and Pricing Research with interactive founder input. | No UI screens exist for business modeling; capabilities are either buried in static text reports or omitted. | S02-EV-003_Workspace_Journey_Sidebar.png | Stages 3-10 | Introduce Stage 2 dedicated sub-views or canvas in workspace for Business Model, Pricing, and Competitor mapping. | Open
S03-DEF-001 | Stage_03 | Financial & Capital Planning | Backend Agent | FCP.1-FCP.10 | Financial Readiness Agent is an Unimplemented Stub in Backend | Architecture / Backend | Critical | P1 | axiora-pulse-be repository | Inspect app/agents/financial_readiness_agent.py | Agent should inherit from BaseAgent, define financial_planning_skill, and compute runway/burn/break-even. | File is an empty placeholder containing only a comment. | app/agents/financial_readiness_agent.py | Stages 4-10 | Implement FinancialReadinessAgent with financial formula engine and register in AGENT_REGISTRY. | Open
S03-DEF-002 | Stage_03 | Financial & Capital Planning | API Layer | FCP.1-FCP.10 | Missing API Endpoints for Stage 3 Financial & Capital Planning | API / Routing | High | P1 | FastAPI router | Query /api/v1/workspaces/{id}/financial | FastAPI should provide GET/POST endpoints for financial models. | Returns HTTP 404 Not Found. | QA REST API curl trace | Stages 4-10 | Add financial router to app/api/v1/ and register in app/main.py. | Open
S03-DEF-003 | Stage_03 | Financial & Capital Planning | Frontend UI | FCP.1-FCP.10 | No Interactive Workspace Screen for Financial & Capital Planning | UI / UX | High | P2 | Workspace view in QA | Click Stage 3 in Journey sidebar | Should open Financial Planning dashboard, capital input forms, and runway simulator. | Stage 3 is a static accordion item that only shows bulleted text. | S03-EV-001_Journey_Stage_State.png | Stages 4-10 | Build FinancialPlanningPage with interactive runway, burn rate, and scenario planning calculators. | Open
S04-DEF-001 | Stage_04 | MVP & Execution Planning | Backend Agent | MVP.1-MVP.8 | MVP & Execution Planning Agent Missing from Backend | Architecture / Backend | Critical | P1 | axiora-pulse-be repository | Search for MVP agent in app/agents/ | MvpPlanningAgent should exist and coordinate feature scoping. | Zero agent files exist for Stage 4. | app/agents/ directory listing | Stages 5-10 | Create app/agents/mvp_planning_agent.py and register in AGENT_REGISTRY. | Open
S04-DEF-002 | Stage_04 | MVP & Execution Planning | API Endpoint | MVP.1-MVP.8 | Missing /workspaces/{id}/mvp Endpoint | API / Routing | High | P1 | FastAPI router | GET /api/v1/workspaces/424/mvp | API endpoint returns MVP feature matrix and sprint roadmap. | Returns HTTP 404 Not Found. | API curl response | Stages 5-10 | Implement router app/api/v1/mvp.py with CRUD and generate operations. | Open
S04-DEF-003 | Stage_04 | MVP & Execution Planning | Frontend UI | MVP.1-MVP.8 | No Interactive Scoping UI for MVP Planning | UI / UX | High | P2 | Workspace view in QA | Click Step 4 in Journey card | Display MoSCoW prioritization board and sprint roadmap timeline. | Static details text only. | S04-EV-001_Journey_Stage_State.png | Stages 5-10 | Build MvpPlanningPage with interactive feature drag-and-drop board. | Open
S05-DEF-001 | Stage_05 | Business Setup & Build Execution | Backend Agent | BSBE.1-BSBE.8 | Business Setup & Build Execution Agent Missing from Backend | Architecture / Backend | Critical | P1 | axiora-pulse-be repository | Inspect app/agents/ | BusinessSetupAgent should exist and evaluate legal/hiring/vendor needs. | No agent file exists. | app/agents/ directory listing | Stages 6-10 | Implement BusinessSetupAgent and add to AGENT_REGISTRY. | Open
S05-DEF-002 | Stage_05 | Business Setup & Build Execution | API Endpoint | BSBE.1-BSBE.8 | Missing /workspaces/{id}/business-setup Endpoint | API / Routing | High | P1 | FastAPI router | GET /api/v1/workspaces/424/business-setup | Returns setup checklist and vendor recommendations. | Returns HTTP 404 Not Found. | API curl response | Stages 6-10 | Create router app/api/v1/business_setup.py. | Open
S05-DEF-003 | Stage_05 | Business Setup & Build Execution | Frontend UI | BSBE.1-BSBE.8 | No Setup Checklist or Vendor Management UI | UI / UX | High | P2 | Workspace view in QA | Click Step 5 in Journey card | Interactive setup checklist with legal, hiring, and tooling recommendations. | Static text only. | S05-EV-001_Journey_Stage_State.png | Stages 6-10 | Build BusinessSetupPage in frontend. | Open
S06-DEF-001 | Stage_06 | Pre-Traction & GTM | Backend Agent | PTGTM.1-PTGTM.8 | GTM Strategy Agent is an Unimplemented Stub in Backend | Architecture / Backend | Critical | P1 | axiora-pulse-be repository | Inspect app/agents/gtm_strategy_agent.py | Agent should inherit from BaseAgent and implement GTM positioning logic. | File is an empty placeholder containing only a comment. | app/agents/gtm_strategy_agent.py | Stages 7-10 | Implement GtmStrategyAgent with beachhead and messaging skills, register in AGENT_REGISTRY. | Open
S06-DEF-002 | Stage_06 | Pre-Traction & GTM | API Endpoint | PTGTM.1-PTGTM.8 | Missing /workspaces/{id}/gtm Endpoint | API / Routing | High | P1 | FastAPI router | GET /api/v1/workspaces/424/gtm | Returns GTM strategy and waitlist analytics. | Returns HTTP 404 Not Found. | API curl response | Stages 7-10 | Implement router app/api/v1/gtm.py. | Open
S06-DEF-003 | Stage_06 | Pre-Traction & GTM | Frontend UI | PTGTM.1-PTGTM.8 | No Interactive GTM or Waitlist Management UI | UI / UX | High | P2 | Workspace view in QA | Click Step 6 in Journey card | Opens GTM campaign and positioning builder. | Static text drawer only. | S06-EV-001_Journey_Stage_State.png | Stages 7-10 | Build GtmStrategyPage in frontend. | Open
S07-DEF-001 | Stage_07 | Testing, Pilot & Improvement | Backend Agent | TPI.1-TPI.8 | Testing, Pilot & Improvement Agent Missing from Backend | Architecture / Backend | Critical | P1 | axiora-pulse-be repository | Inspect app/agents/ | TestingPilotAgent should exist and compute Launch Readiness Score. | No agent file exists. | app/agents/ directory listing | Stages 8-10 | Implement TestingPilotAgent and register in AGENT_REGISTRY. | Open
S07-DEF-002 | Stage_07 | Testing, Pilot & Improvement | API Endpoint | TPI.1-TPI.8 | Missing /workspaces/{id}/pilot Endpoint | API / Routing | High | P1 | FastAPI router | GET /api/v1/workspaces/424/pilot | Returns pilot metrics, feedback summary, and launch readiness score. | Returns HTTP 404 Not Found. | API curl response | Stages 8-10 | Create router app/api/v1/pilot.py. | Open
S07-DEF-003 | Stage_07 | Testing, Pilot & Improvement | Frontend UI | TPI.1-TPI.8 | No Pilot Governance or Launch Readiness Dashboard | UI / UX | High | P2 | Workspace view in QA | Click Step 7 in Journey card | Display beta cohort tracking and Launch Readiness Score gauge. | Static text only. | S07-EV-001_Journey_Stage_State.png | Stages 8-10 | Build TestingPilotPage in frontend. | Open
S08-DEF-001 | Stage_08 | Launch, Traction & Customer Validation | Backend Agent | LTCV.1-LTCV.8 | Launch & Customer Validation Agent Missing from Backend | Architecture / Backend | Critical | P1 | axiora-pulse-be repository | Inspect app/agents/ | CommercialLaunchAgent should exist and track revenue/retention/PMF. | No agent file exists. | app/agents/ directory listing | Stages 9-10 | Implement CommercialLaunchAgent and register in AGENT_REGISTRY. | Open
S08-DEF-002 | Stage_08 | Launch, Traction & Customer Validation | API Endpoint | LTCV.1-LTCV.8 | Missing /workspaces/{id}/launch Endpoint | API / Routing | High | P1 | FastAPI router | GET /api/v1/workspaces/424/launch | Returns acquisition funnel, conversion metrics, and PMF score. | Returns HTTP 404 Not Found. | API curl response | Stages 9-10 | Create router app/api/v1/launch.py. | Open
S08-DEF-003 | Stage_08 | Launch, Traction & Customer Validation | Frontend UI | LTCV.1-LTCV.8 | No Commercial Launch or Traction Analytics Dashboard | UI / UX | High | P2 | Workspace view in QA | Click Step 8 in Journey card | Display revenue, CAC, LTV, churn, and PMF signals. | Static text only. | S08-EV-001_Journey_Stage_State.png | Stages 9-10 | Build LaunchTractionPage in frontend. | Open
S09-DEF-001 | Stage_09 | Break-Even & Growth | Backend Agent | BEG.1-BEG.8 | Break-Even & Growth Agent Missing from Backend | Architecture / Backend | Critical | P1 | axiora-pulse-be repository | Inspect app/agents/ | BreakEvenGrowthAgent should exist and compute margin expansion. | No agent file exists. | app/agents/ directory listing | Stages 10-10 | Implement BreakEvenGrowthAgent and register in AGENT_REGISTRY. | Open
S09-DEF-002 | Stage_09 | Break-Even & Growth | API Endpoint | BEG.1-BEG.8 | Missing /workspaces/{id}/growth Endpoint | API / Routing | High | P1 | FastAPI router | GET /api/v1/workspaces/424/growth | Returns break-even trajectory and cost reduction recommendations. | Returns HTTP 404 Not Found. | API curl response | Stages 10-10 | Create router app/api/v1/growth.py. | Open
S09-DEF-003 | Stage_09 | Break-Even & Growth | Frontend UI | BEG.1-BEG.8 | No Break-Even Tracking or Growth Experimentation Dashboard | UI / UX | High | P2 | Workspace view in QA | Click Step 9 in Journey card | Display break-even trajectory, margin analysis, and ICE experiment backlog. | Static text only. | S09-EV-001_Journey_Stage_State.png | Stages 10-10 | Build BreakEvenGrowthPage in frontend. | Open
S10-DEF-001 | Stage_10 | Scale, Expansion & Strategic Future | Backend Agent | SESF.1-SESF.8 | Scale & Strategic Future Agent Missing from Backend | Architecture / Backend | Critical | P1 | axiora-pulse-be repository | Inspect app/agents/ | StrategicScaleAgent should exist and model investor readiness/exit options. | No agent file exists. | app/agents/ directory listing | N/A | Implement StrategicScaleAgent and register in AGENT_REGISTRY. | Open
S10-DEF-002 | Stage_10 | Scale, Expansion & Strategic Future | API Endpoint | SESF.1-SESF.8 | Missing /workspaces/{id}/scale Endpoint | API / Routing | High | P1 | FastAPI router | GET /api/v1/workspaces/424/scale | Returns investor readiness score, valuation models, and exit strategies. | Returns HTTP 404 Not Found. | API curl response | N/A | Create router app/api/v1/scale.py. | Open
S10-DEF-003 | Stage_10 | Scale, Expansion & Strategic Future | Frontend UI | SESF.1-SESF.8 | No Strategic Scaling or Investor Data Room UI | UI / UX | High | P2 | Workspace view in QA | Click Step 10 in Journey card | Display investor readiness dashboard and expansion modeling tools. | Static text only. | S10-EV-001_Journey_Stage_State.png | N/A | Build ScaleExpansionPage in frontend. | Open