## Executive Summary
AXIORA PULSE — END-TO-END QA AUDIT & LIFECYCLE SUMMARY
Master Executive Evaluation across all 10 Development Stages ¦ QA URL: https://qa.axiorapulse.com
Platform Name | Axiora Pulse — Autonomous Startup Mentorship & Validation Engine
QA Environment URL | https://qa.axiorapulse.com/login
Authenticated User | ntortj@gmail.com (Role: member)
Active Test Workspaces | Workspace 424 ('Idea') ¦ Workspace 416 ('AI mentor')
Evaluated Application | AI Boss (Autonomous Organizational Management & Coordination Engine)
Audit Date | 2026-10-22
Evaluation Authority | Autonomous QA Lead, Senior Business Analyst & Evaluator
Overall Platform Readiness | STAGES 1-2 OPERATIONAL (WITH GATES) ¦ STAGES 3-10 ARCHITECTURALLY BLOCKED
EXECUTIVE SUMMARY FINDINGS
Current System Reality | Axiora Pulse currently implements a 2-stage operational journey in both frontend and backend. Stage 1 (Idea Validation) is fully implemented with automated validation scoring, certificate issuance, and PDF reporting. Stage 2 (Market Research & Business Model) is partially implemented with backend agents (MarketResearchAgent and SurveyIntelligenceAgent) and frontend survey routes, but lacks an unprompted empty-state CTA and has no dedicated business model canvas.
Status of Stages 3 through 10 | Stages 3 through 10 (Financial Planning, MVP Scoping, Business Setup, GTM, Testing/Pilot, Launch/Traction, Break-Even/Growth, and Scale/Expansion) are extensively documented in product specification workbooks (over 1,600 capability definitions in Docs/), but are NOT functionally implemented in the live application. Backend agent files for Stages 3 and 6 are empty 2-line placeholder stubs, and no agent files exist for Stages 4, 5, 7, 8, 9, 10. In frontend planFeatures.ts, AVAILABLE_JOURNEY_STAGES is hardcoded to 2, and Stages 3-10 are explicitly configured as comingSoon: true.
Data Persistence Architecture | The database schema (PostgreSQL) has pre-allocated JSON columns for all 10 stages in the workspaces table (validation_result, financial_result, mvp_result, business_setup_result, gtm_result, test_pilot_result, launch_traction_result, break_even_growth_result, scale_expansion_result). All columns for Stages 3-10 currently evaluate to NULL. This confirms forward architectural intent, but zero data populates these fields.
Critical Cross-Stage Bottleneck | Because Stages 3 through 10 lack API routers (HTTP 404) and backend orchestration planners, any automated handoff from Stage 2 downstream is completely severed. The platform safely prevents invalid progression by keeping these stages in a 'Pending' / 'Coming Soon' state in the UI.

## 10-Stage Lifecycle Map
AXIORA PULSE — AUTHORITATIVE 10-STAGE DEVELOPMENT LIFECYCLE
Complete lifecycle definition, official stage names, business objectives, and implementation status
Stage ID | Official Stage Name | Business Objective | Entry Criteria | Exit Criteria | Relevant Agents | Documented Source | Implementation Status | QA Audit Disposition
Stage_01 | Idea Validation | Validate startup idea, customer problem clarity, value prop, feasibility, and Go/Pivot verdict | Founder submits idea context via chat/voice | Idea Validation Score, Verdict, Certificate, PDF Report | IdeaValidationAgent, ARYA AI Mentor | Docs/Idea Validation - Capabilities.xlsx, TESTING_Idea_Validation.xlsx | Implemented and Available | Validated (Reference Stage)
Stage_02 | Market Research & Business Model | Target customer profiling, market sizing, ICP, competitor mapping, survey intelligence, and unit economics | Stage 1 validated idea and problem statement | Primary ICP, competitor matrix, survey sentiment, and revenue model | MarketResearchAgent, SurveyIntelligenceAgent | Docs/Market Strategy Agent.xlsx, Docs/Survey Intelligence Agent (1).xlsx | Partially Implemented | Validated with Limitations
Stage_03 | Financial & Capital Planning | Capital requirements, founder survival runway, monthly burn, revenue projections, and break-even target | Stage 2 ICP, pricing model, and customer willingness to pay | Runway in months, monthly burn rate, break-even target date, funding gap | FinancialReadinessAgent (Stub) | Docs/Financial & Capital Planning (1).xlsx | Documented but not implemented | Not Validated — Blocked
Stage_04 | MVP & Execution Planning | POC vs MVP requirements, MoSCoW feature scoping, tech stack selection, and sprint roadmap | Stage 3 capital plan and validated core problem/solution | MVP feature scope (Must-haves), architecture plan, 6-week sprint roadmap | MVP & Execution Planning Agent | Docs/MVP & Execution Planning.xlsx | Documented but not implemented | Not Validated — Blocked
Stage_05 | Business Setup & Build Execution | Team hiring, co-founder/agency decisions, job descriptions, legal incorporation timing, and build monitoring | Stage 4 MVP feature specification and delivery mode | Legal entity structure, core team scorecard, vendor contracts, build velocity | Business Setup & Build Execution Agent | Docs/Business Setup & Build Execution.xlsx | Documented but not implemented | Not Validated — Blocked
Stage_06 | Pre-Traction & GTM | Beachhead customer selection, brand positioning, landing page messaging, waitlist, and founder content | Stage 5 build progress and Stage 2 ICP definition | Live waitlist, community channels, founder content pillars, early pre-sales | GtmStrategyAgent (Stub) | Docs/V2 - PRE Traction & GTM.xlsx, Docs/Market Strategy Agent.xlsx | Documented but not implemented | Not Validated — Blocked
Stage_07 | Testing, Pilot & Improvement | QA, UAT testing, beta pilot cohort recruitment, usability testing, bug triage, and Launch Readiness Score | Stage 5/6 release candidate and pilot cohort | UAT sign-off, triaged bug backlog, Launch Readiness Score and verdict | Testing, Pilot & Improvement Agent | Docs/Testing, Pilot & Improvement (1).xlsx | Documented but not implemented | Not Validated — Blocked
Stage_08 | Launch, Traction & Customer Validation | Commercial launch rollout, customer acquisition, sales execution, revenue tracking, CAC/LTV, and PMF signals | Stage 7 Launch Readiness sign-off and approved release | Paying customers, MRR/ARR, customer retention curve, Sean Ellis PMF score | Commercial Launch & Traction Agent | Docs/Launch, Traction & Customer Validation (1).xlsx | Documented but not implemented | Not Validated — Blocked
Stage_09 | Break-Even & Growth | Break-even monitoring, revenue optimization, cost reduction, gross margin expansion, and growth experiments | Stage 8 paying customers and initial unit economics | Monthly net profitability, reduced CAC, expansion revenue, ICE experiment log | Break-Even & Growth Agent | Docs/Break Even & Growth (1).xlsx | Documented but not implemented | Not Validated — Blocked
Stage_10 | Scale, Expansion & Strategic Future | Org scaling, executive leadership, SOP standardization, new markets, fundraising, and exit strategy | Stage 9 sustainable profitability and positive cash flow | International expansion plan, investor data room, valuation model, exit roadmap | Strategic Scale & Enterprise Expansion Agent | Docs/Scale, Expansion & Strategic Future (1).xlsx | Documented but not implemented | Not Validated — Blocked

## Cross-Stage Metrics Dashboard
AXIORA PULSE — CROSS-STAGE QA METRICS & COVERAGE
Comparative breakdown of test execution, pass rates, capability coverage, and defects per stage
Stage ID | Official Stage Name | Identified Tests | Executed | Passed | Failed | Blocked | Partial | Pass Rate (%) | Doc Capabilities | Implemented Caps | Critical Defects | High Defects | Medium Defects | Low Defects | Final Status
Stage_01 | Idea Validation (Reference) | 35 | 35 | 27 | 4 | 1 | 3 | 77.1% | 146 | 120 | 1 | 3 | 5 | 2 | Validated with Observations
Stage_02 | Market Research & Business Model | 10 | 10 | 9 | 1 | 0 | 0 | 90.0% | 10 | 8 | 0 | 1 | 1 | 0 | VALIDATED WITH LIMITATIONS (LIVE TESTED)
Stage_03 | Financial & Capital Planning | 8 | 8 | 4 | 4 | 0 | 0 | 50.0% | 10 | 0 | 1 | 2 | 0 | 0 | BLOCKED — NOT IMPLEMENTED (LIVE VERIFIED)
Stage_04 | MVP & Execution Planning | 5 | 5 | 1 | 4 | 0 | 0 | 20.0% | 8 | 0 | 1 | 2 | 0 | 0 | BLOCKED — NOT IMPLEMENTED (LIVE VERIFIED)
Stage_05 | Business Setup & Build Execution | 5 | 5 | 1 | 4 | 0 | 0 | 20.0% | 8 | 0 | 1 | 2 | 0 | 0 | BLOCKED — NOT IMPLEMENTED (LIVE VERIFIED)
Stage_06 | Pre-Traction & GTM | 5 | 5 | 1 | 4 | 0 | 0 | 20.0% | 8 | 0 | 1 | 2 | 0 | 0 | BLOCKED — NOT IMPLEMENTED (LIVE VERIFIED)
Stage_07 | Testing, Pilot & Improvement | 5 | 5 | 1 | 4 | 0 | 0 | 20.0% | 8 | 0 | 1 | 2 | 0 | 0 | BLOCKED — NOT IMPLEMENTED (LIVE VERIFIED)
Stage_08 | Launch, Traction & Customer Validation | 5 | 5 | 1 | 4 | 0 | 0 | 20.0% | 8 | 0 | 1 | 2 | 0 | 0 | BLOCKED — NOT IMPLEMENTED (LIVE VERIFIED)
Stage_09 | Break-Even & Growth | 5 | 5 | 1 | 4 | 0 | 0 | 20.0% | 8 | 0 | 1 | 2 | 0 | 0 | BLOCKED — NOT IMPLEMENTED (LIVE VERIFIED)
Stage_10 | Scale, Expansion & Strategic Future | 5 | 5 | 1 | 4 | 0 | 0 | 20.0% | 8 | 0 | 1 | 2 | 0 | 0 | BLOCKED — NOT IMPLEMENTED (LIVE VERIFIED)

## Dependencies & Arch Gaps
AXIORA PULSE — CROSS-STAGE DEPENDENCIES & ARCHITECTURAL GAPS
Critical gaps in upstream-to-downstream handoffs, agent orchestration, and stage transition gates
Gap ID | Upstream Stage | Downstream Stage | Handoff Deliverable | Architectural Defect / Failure Mode | Impact on Founder Experience | Required Architecture Fix
GAP-01 | Stage 1 (Idea Validation) | Stage 2 (Market Research) | Validated Idea & Problem Statement | Survey generation is disabled until validation runs, but no guidance or trigger CTA is shown on the Survey tab. | Founder clicks Survey Intelligence tab and sees empty 'No surveys found' screen with no path forward. | Add proactive CTA on Survey tab prompting the user to complete Idea Validation first.
GAP-02 | Stage 2 (Market Research) | Stage 3 (Financial Planning) | ICP Pricing, Willingness to Pay, and Target Market Size | Stage 3 backend agent is an empty stub. No API exists to receive Stage 2 pricing data. | Founder cannot translate validated customer pricing into runway or revenue projections. | Implement FinancialReadinessAgent and connect it to context_builder output from Stage 2.
GAP-03 | Stage 3 (Financial Planning) | Stage 4 (MVP Planning) | Runway Budget and Safe Development Capital | Stage 4 has zero backend agent code and no MoSCoW scoping engine. | Founder cannot constrain MVP feature scope to fit actual available development budget. | Build MvpPlanningAgent with MoSCoW categorization skill constrained by Stage 3 budget.
GAP-04 | Stage 4 (MVP Planning) | Stage 5 (Business Setup) | MVP Architecture, Delivery Mode, and Tech Stack | Stage 5 has no agent or hiring/vendor evaluation engine. | Founder cannot transition tech stack recommendations into job descriptions or contractor contracts. | Build BusinessSetupAgent to ingest Stage 4 tech stack and generate required roles.
GAP-05 | Stage 5 (Business Setup) | Stage 6 (Pre-Traction) | Operational Entity, Brand Assets, and Team Readiness | Stage 6 backend agent is an empty stub. | Founder cannot build pre-traction waitlist or launch community before release. | Implement GtmStrategyAgent and connect beachhead segmentation with Stage 2 ICP.
GAP-06 | Stage 6 (Pre-Traction) | Stage 7 (Testing & Pilot) | Waitlist Cohort and Pre-Registered Beta Users | Stage 7 has no pilot tracking engine or Launch Readiness score. | Founder cannot recruit beta users from waitlist or measure launch readiness objectively. | Build TestingPilotAgent with Launch Readiness Scoring (0-100) algorithm.
GAP-07 | Stage 7 (Testing & Pilot) | Stage 8 (Launch & Traction) | Signed-off Release Candidate and Pilot Feedback | Stage 8 has no commercial launchpad or PMF detector. | Founder cannot track commercial launch conversion, CAC, or churn. | Build CommercialLaunchAgent with cohort retention and revenue analytics.
GAP-08 | Stage 8 (Launch & Traction) | Stage 9 (Break-Even & Growth) | Paying Customers, MRR, Churn, and Unit Economics | Stage 9 has no break-even tracking or margin expansion engine. | Founder cannot identify cost leaks or optimize marketing ROI to reach profitability. | Build BreakEvenGrowthAgent with ICE growth experimentation backlog.
GAP-09 | Stage 9 (Break-Even & Growth) | Stage 10 (Scale & Expansion) | Sustainable Profitability, Positive Cash Flow, and SOPs | Stage 10 has no investor data room or international expansion engine. | Founder cannot prepare institutional fundraising diligence or evaluate exit options. | Build StrategicScaleAgent with data room assembly and valuation modeling.

## Lifecycle Progression Plan
AXIORA PULSE — LIFECYCLE PROGRESSION & REMEDIATION ROADMAP
Phased engineering roadmap to unblock Stages 3 through 10 and achieve end-to-end lifecycle validity
Phase | Target Stages | Primary Engineering Deliverable | Target Agent(s) to Build | API & DB Actions | Frontend Work Required | Expected QA Exit Gate
Phase 1 Polish | Stage 2 (Market Research) | Fix Survey empty state and surface Business Model canvas | SurveyIntelligenceAgent, MarketResearchAgent | Expose PUT /surveys/workspace/{id} and GET /market-research | Add empty state CTA on Survey tab; create Business Model sub-view | Stage 2 achieves 100% test pass rate with unprompted UX.
Phase 2A | Stage 3 (Financial) & Stage 4 (MVP) | Implement Capital Planning and MVP MoSCoW scoping engines | FinancialReadinessAgent, MvpPlanningAgent | Build /api/v1/workspaces/{id}/financial and /mvp routers | Create FinancialPlanningPage and MvpScopingPage components | Stages 3 & 4 advance from 'Coming Soon' to 'Active' in Journey.
Phase 2B | Stage 5 (Setup) & Stage 6 (GTM) | Implement Business Setup and GTM Pre-Traction launchpad | BusinessSetupAgent, GtmStrategyAgent | Build /api/v1/workspaces/{id}/business-setup and /gtm routers | Create BusinessSetupPage and GtmStrategyPage with waitlist UI | Stages 5 & 6 operational with passing E2E test runs.
Phase 3A | Stage 7 (Testing) & Stage 8 (Launch) | Implement Launch Readiness scoring and commercial traction engine | TestingPilotAgent, CommercialLaunchAgent | Build /api/v1/workspaces/{id}/pilot and /launch routers | Build PilotDashboard and TractionRevenuePage components | Stage 7 Launch Readiness verdict accurately gates Stage 8 launch.
Phase 3B | Stage 9 (Break-Even) & Stage 10 (Scale) | Implement Break-Even optimization and Enterprise Scale suite | BreakEvenGrowthAgent, StrategicScaleAgent | Build /api/v1/workspaces/{id}/growth and /scale routers | Build BreakEvenDashboard and StrategicDataRoom components | Full 10-stage lifecycle operational from Idea to Scaling.