## INDEX & Executive Summary
AXIORA PULSE — QUALITY ASSURANCE & AUDIT REPORT
Stage 05: Business Setup & Build Execution ¦ Reference Concept: AI Boss (Autonomous Organizational Platform)
METADATA ATTRIBUTE | DETAILS / SPECIFICATION
Official Stage ID | Stage_05
Official Stage Name | Business Setup & Build Execution
Execution Date | 2026-10-22
QA Target URL | https://qa.axiorapulse.com/login
Test Execution Lead | Antigravity Autonomous QA Lead & Evaluation Agent
Active QA Account | ntortj@gmail.com
Target Workspace | Workspace ID: 424 ('Idea') / Workspace ID: 416 ('AI mentor')
Evaluated Application | AI Boss (Autonomous Organizational Management & Coordination Engine)
Overall Stage Status | BLOCKED — NOT IMPLEMENTED (LIVE VERIFIED)
Final Stage Assessment | Not Validated — Documented but Not Implemented
SECTION 1 — EXECUTIVE SUMMARY
Testing Scope & Mandate | Comprehensive functional, agent-level, architectural, and workflow evaluation of Stage 05 (Business Setup & Build Execution) against authoritative product specifications, local codebase, and the live QA environment.
Key Findings | Stage 5 output was verified live in Workspace 424. The business_setup_result column in the database evaluates to NULL. There is no backend agent, no API router (/api/v1/workspaces/424/business-setup returns 404), and no frontend setup or hiring dashboard.
Critical Blockers | 1. No backend agent in app/agents/ for business setup or build tracking. 2. API route /api/v1/workspaces/{id}/business-setup returns 404. 3. Frontend has no legal/hiring/vendor management views. 4. Stage 5 in Journey card is an un-interactive informational drawer.
Progression Recommendation | Stage 05 cannot be signed off for general release. Address critical defects and implement the missing agent/API/UI layer before opening this stage in the user journey.
SECTION 2 — STAGE OVERVIEW & LIFECYCLE CONTEXT
Business Objective | Hiring technical & non-technical team, co-founder/agency decisions, job descriptions, legal entity registration timing, compliance/contracts, tool/vendor selection, and build execution monitoring.
Entry Criteria | Completion of Stage 4 with verified status and approval gate passed.
Exit Criteria | Validated Stage 05 artifacts, approved stage verdict, and prerequisite handoff data published.
Relevant Agents | Business Setup & Build Execution Agent (Docs/Business Setup & Build Execution.xlsx)
Upstream Dependencies | Stage 4 deliverables and Strategic Memory state.
Downstream Handoffs | Stage 6 input context and audit traces.
SECTION 12 — FINAL STAGE READINESS ASSESSMENT
Final Disposition | Not Validated — Documented but Not Implemented
Assessment Rationale | Implement BusinessSetupAgent in backend, integrate legal structure guidelines and vendor recommendation skill, expose REST endpoints, and build setup dashboard in frontend.
WORKBOOK TABLE OF CONTENTS
Sheet No. | Worksheet Name | Mandatory Section(s) Covered | Content Description
1 | INDEX & Executive Summary | Sections 1, 2, 12 | Executive Summary, Stage Overview, and Final Assessment
2 | QA Dashboard & Metrics | Section 10 | Test execution metrics, pass rates, requirement & defect coverage
3 | Capability Audit | Section 3 | Capability and requirement traceability matrix against product docs
4 | Agent & Workflow Tests | Sections 5, 6 | Agent-level verification, prompt pipeline, and workflow handoffs
5 | Test Execution and Evidence | Sections 4, 7, 9 | Detailed test procedures, negative/boundary tests, and evidence log
6 | Defect Register | Section 8 | Comprehensive defect register with severity, priority, and repro steps
7 | DEV Fix and Retest | Section 11 | Remediation plan, developer action tracker, and retest procedures

## QA Dashboard & Metrics
STAGE 05 — QA EXECUTION DASHBOARD & METRICS
Stage: Business Setup & Build Execution ¦ Target: QA Environment (https://qa.axiorapulse.com)
CATEGORY | METRIC NAME | VALUE | REMARKS / BASIS
Test Execution Metrics | Total Identified Test Cases | 5 | Formal test cases specified
Test Execution Metrics | Total Executed Test Cases | 5 | Cases executed against QA and codebase
Test Execution Metrics | Passed Test Cases | 1 | Acceptance criteria fully met with evidence
Test Execution Metrics | Failed Test Cases | 4 | Material defect or functional absence confirmed
Test Execution Metrics | Blocked Test Cases | 0 | Execution blocked by missing prerequisite/feature
Test Execution Metrics | Partial Test Cases | 0 | Partially functional / incomplete behavior
Test Execution Metrics | Untested Test Cases | 0 | Unexecuted scenarios
Test Execution Metrics | Executed Test Pass Rate | 20.0% | Passed / Executed Cases
Capability Coverage | Total Documented Capabilities | 8 | From Docs specification sheets
Capability Coverage | Implemented / Available Capabilities | 0 | Operational in codebase / QA
Capability Coverage | Capability Implementation Coverage | 0.0% | Implemented / Documented
Defect Summary | Critical (P1) Defects | 1 | Blocks stage execution / Missing core agent
Defect Summary | High (P2) Defects | 2 | Major feature failure or missing workflow API
Defect Summary | Medium (P3) Defects | 0 | Usability, navigation, or data presentation defect
Defect Summary | Low (P4) Defects | 0 | Minor cosmetic or text inconsistency

## Capability Audit
STAGE 05 — CAPABILITY & REQUIREMENT AUDIT MATRIX
Traceability matrix between product capability specifications in Docs/ and implementation in QA
Capability ID | Capability Name | Architectural Layer | Responsible Agent | Documented Expected Behaviour | Implementation Status | Actual QA Application Evidence | Audit Disposition
BSBE.1 | Legal Entity Formation & Timing Advisor | Layer 1 | Business Setup Agent | Advise on exact timing and structure for company incorporation (LLC/Pvt Ltd/C-Corp) | Documented but not implemented | Verified live: business_setup_result is NULL in database. | Blocked
BSBE.2 | Founder Agreements & Vesting Governance | Layer 2 | Business Setup Agent | Generate founder equity split frameworks, vesting schedules, and IP assignment clauses | Documented but not implemented | No agent or backend service exists. | Blocked
BSBE.3 | Team Roles & Capacity Planning | Layer 3 | Business Setup Agent | Identify critical first-hire roles vs outsourced tasks based on founder skill gaps | Documented but not implemented | No agent or backend service exists. | Blocked
BSBE.4 | Automated Job Description & Scorecard Generator | Layer 4 | Business Setup Agent | Generate outcome-oriented job descriptions and candidate evaluation rubrics | Documented but not implemented | No agent or backend service exists. | Blocked
BSBE.5 | Vendor, Contractor & Agency Evaluation | Layer 5 | Business Setup Agent | Provide vendor evaluation criteria, contract templates, and milestone payment schedules | Documented but not implemented | No agent or backend service exists. | Blocked
BSBE.6 | Software Stack & Operational Tool Selection | Layer 6 | Business Setup Agent | Curate recommended software stack (CRM, PM, analytics, hosting, accounting) | Documented but not implemented | No agent or backend service exists. | Blocked
BSBE.7 | Compliance, Privacy & Regulatory Baseline | Layer 7 | Business Setup Agent | Verify basic regulatory compliance (GDPR/DPDP consent, Terms of Use, IP protection) | Documented but not implemented | No agent or backend service exists. | Blocked
BSBE.8 | Build Execution Monitoring & Velocity Tracking | Layer 8 | Build Execution Agent | Track progress against Stage 4 MVP roadmap and surface delays or cost overruns | Documented but not implemented | No agent or backend service exists. | Blocked

## Agent & Workflow Tests
STAGE 05 — AGENT-LEVEL & WORKFLOW EVALUATION
Evaluation of agent availability, orchestration, prompt pipelines, and workflow state transitions
AGENT-LEVEL EVALUATION
Agent Name | Documented Responsibility | Doc Reference | Availability in Codebase | Test Inputs (AI Boss Context) | Expected Output Structure | Actual Observed Output | Verification Result | Defect / Architectural Finding
Business Setup & Build Execution Agent (Docs/Business Setup & Build Execution.xlsx) | Execute stage activities for Business Setup & Build Execution | Docs/Business Setup & Build Execution.xlsx | Not Implemented (Missing from app/agents/) | AI Boss: Stage 5 test scenario execution | Structured stage deliverable and Stage 6 prerequisite handoff | Zero backend agent file, zero API router, zero database execution logic. | BLOCKED | S05-DEF-001: Agent not implemented in backend
WORKFLOW & INTEGRATION EVALUATION
Workflow Scenario | Preconditions | Trigger / Action | Observed State Transition | Data Persistence Result | Integration Handoff Result | Status
Stage 05 Entry Gate Check | Stage 4 incomplete | Founder attempts to start Stage 5 | Stage remains Pending / Locked; directs founder to Stage 4 | Workspace state preserved in database | Upstream prerequisite enforcement confirmed | PASS
Stage 05 Execution Trigger | Stage 4 validated | Trigger Stage 05 action via API or UI | No API or UI trigger exists; operation rejected with 404 | Field remains NULL in database | Handoff to downstream stages blocked | FAIL
Stage 05 Data Integrity Across Reload | Workspace active in QA | Reload page or query state API | Workspace state reloaded cleanly without corruption | State perfectly persisted in PostgreSQL database | JWT session preserved | PASS

## Test Execution and Evidence
STAGE 05 — DETAILED TEST EXECUTION & EVIDENCE REGISTER
Full test scenario procedures, execution logs, expected vs actual results, and evidence links
Test Case ID | Test Category | Layer | Capability ID(s) | Test Objective / Scenario | Preconditions & Test Data | Detailed Execution Steps | Expected Result | Actual Result | Execution Status | Defect Reference | Evidence File Reference
S05-TC-001 | Architecture / Codebase | Layer 1-8 | BSBE.1-BSBE.8 | Verify Backend Business Setup Agent Implementation | axiora-pulse-be codebase | Search app/agents/ for business_setup_agent.py | Agent present and registered in AGENT_REGISTRY | No agent exists for Stage 5 in backend. | FAIL | S05-DEF-001 | app/agents/ directory listing
S05-TC-002 | API Availability | Layer 1-8 | BSBE.1-BSBE.8 | Query Workspace Business Setup Endpoint | QA URL and auth token | GET https://qa.axiorapulse.com/api/v1/workspaces/424/business-setup | 200 OK or 400 with prerequisites | HTTP 404 Not Found. | FAIL | S05-DEF-002 | API curl response
S05-TC-003 | UI / Journey Sidebar | Shared Platform | BSBE.1 | Verify Stage 5 in Journey Sidebar | Workspace 424 open in QA | Click Step 5 'Business Setup & Build Execution' | Opens setup checklist or hiring planner | Static text drawer with bullet points. No actionable workflow. | FAIL | S05-DEF-003 | S05-EV-001_Journey_Stage_State.png
S05-TC-004 | Data Schema | Layer 1 | BSBE.1 | Verify Database Column for Business Setup Results | axiora-pulse-be models | Check Workspace model in app/db/models.py | business_setup_result JSON column exists | Column exists: business_setup_result = Column(JSON, nullable=True). Evaluates to NULL in QA. | PASS |  | app/db/models.py:230
S05-TC-005 | Live Output Validation | Layer 1-8 | BSBE.1 | Validate Stage 5 Output Presence Post-Validation | Workspace 424 state API | GET /api/v1/workspaces/424/state -> business_setup_result | Business setup checklist populated | business_setup_result is None. Confirms zero Stage 5 output generation. | FAIL | S05-DEF-001 | Workspace 424 state JSON

## Defect Register
STAGE 05 — DEFECT REGISTER
Recorded defects, severity classification, reproduction steps, evidence, and remediation
Defect ID | Module / Area | Capability Reference | Defect Title | Defect Category | Severity | Priority | Preconditions | Reproduction Steps | Expected Result | Actual Result | Evidence Reference | Recommended Remediation | Retest Status
S05-DEF-001 | Backend Agent | BSBE.1-BSBE.8 | Business Setup & Build Execution Agent Missing from Backend | Architecture / Backend | Critical | P1 | axiora-pulse-be repository | Inspect app/agents/ | BusinessSetupAgent should exist and evaluate legal/hiring/vendor needs. | No agent file exists. | app/agents/ directory listing | Implement BusinessSetupAgent and add to AGENT_REGISTRY. | Open
S05-DEF-002 | API Endpoint | BSBE.1-BSBE.8 | Missing /workspaces/{id}/business-setup Endpoint | API / Routing | High | P1 | FastAPI router | GET /api/v1/workspaces/424/business-setup | Returns setup checklist and vendor recommendations. | Returns HTTP 404 Not Found. | API curl response | Create router app/api/v1/business_setup.py. | Open
S05-DEF-003 | Frontend UI | BSBE.1-BSBE.8 | No Setup Checklist or Vendor Management UI | UI / UX | High | P2 | Workspace view in QA | Click Step 5 in Journey card | Interactive setup checklist with legal, hiring, and tooling recommendations. | Static text only. | S05-EV-001_Journey_Stage_State.png | Build BusinessSetupPage in frontend. | Open

## DEV Fix and Retest
STAGE 05 — REMEDIATION & RETEST TRACKER
Action items, developer ownership, priority, retest procedures, and exit gates
Action ID | Source Type | Defect Reference | Capability IDs | Action Title | Required DEV Action | Priority | DEV Owner | DEV Status | Retest Procedure | Exit Gate
ACT-Stage_05-001 | Confirmed Defect | S05-DEF-001 | BSBE.1-BSBE.8 | Business Setup & Build Execution Agent Missing from Backend | Implement BusinessSetupAgent and add to AGENT_REGISTRY. | P1 | Backend / AI Team | TODO - Fix Required | Execute S05-DEF-001 reproduction steps in QA environment after build deployment. | Passing automated test and verified evidence in Stage 05 report.
ACT-Stage_05-002 | Confirmed Defect | S05-DEF-002 | BSBE.1-BSBE.8 | Missing /workspaces/{id}/business-setup Endpoint | Create router app/api/v1/business_setup.py. | P1 | Frontend / UI Team | TODO - Fix Required | Execute S05-DEF-002 reproduction steps in QA environment after build deployment. | Passing automated test and verified evidence in Stage 05 report.
ACT-Stage_05-003 | Confirmed Defect | S05-DEF-003 | BSBE.1-BSBE.8 | No Setup Checklist or Vendor Management UI | Build BusinessSetupPage in frontend. | P2 | Frontend / UI Team | TODO - Fix Required | Execute S05-DEF-003 reproduction steps in QA environment after build deployment. | Passing automated test and verified evidence in Stage 05 report.