## INDEX & Executive Summary
AXIORA PULSE — QUALITY ASSURANCE & AUDIT REPORT
Stage 06: Pre-Traction & GTM ¦ Reference Concept: AI Boss (Autonomous Organizational Platform)
METADATA ATTRIBUTE | DETAILS / SPECIFICATION
Official Stage ID | Stage_06
Official Stage Name | Pre-Traction & GTM
Execution Date | 2026-10-22
QA Target URL | https://qa.axiorapulse.com/login
Test Execution Lead | Antigravity Autonomous QA Lead & Evaluation Agent
Active QA Account | ntortj@gmail.com
Target Workspace | Workspace ID: 424 ('Idea') / Workspace ID: 416 ('AI mentor')
Evaluated Application | AI Boss (Autonomous Organizational Management & Coordination Engine)
Overall Stage Status | BLOCKED — NOT IMPLEMENTED (LIVE VERIFIED)
Final Stage Assessment | Not Validated — Documented but Not Implemented
SECTION 1 — EXECUTIVE SUMMARY
Testing Scope & Mandate | Comprehensive functional, agent-level, architectural, and workflow evaluation of Stage 06 (Pre-Traction & GTM) against authoritative product specifications, local codebase, and the live QA environment.
Key Findings | Stage 6 output was evaluated live in Workspace 424. The gtm_result column in the database evaluates to NULL. Backend agent file app/agents/gtm_strategy_agent.py is an empty stub. The API endpoint /api/v1/workspaces/424/gtm returns HTTP 404.
Critical Blockers | 1. Backend agent app/agents/gtm_strategy_agent.py is an empty placeholder. 2. API route /api/v1/workspaces/{id}/gtm returns 404. 3. Frontend has no GTM planning, waitlist management, or positioning canvas. 4. Stage 6 in Journey card is an un-interactive informational drawer.
Progression Recommendation | Stage 06 cannot be signed off for general release. Address critical defects and implement the missing agent/API/UI layer before opening this stage in the user journey.
SECTION 2 — STAGE OVERVIEW & LIFECYCLE CONTEXT
Business Objective | Beachhead customer selection, brand positioning, messaging, landing page guidance, waitlist creation, WhatsApp/social community building, founder content, educational lead generation, and pre-sales.
Entry Criteria | Completion of Stage 5 with verified status and approval gate passed.
Exit Criteria | Validated Stage 06 artifacts, approved stage verdict, and prerequisite handoff data published.
Relevant Agents | GTM Strategy Agent (app/agents/gtm_strategy_agent.py), Market Strategy Agent (Docs/Market Strategy Agent.xlsx)
Upstream Dependencies | Stage 5 deliverables and Strategic Memory state.
Downstream Handoffs | Stage 7 input context and audit traces.
SECTION 12 — FINAL STAGE READINESS ASSESSMENT
Final Disposition | Not Validated — Documented but Not Implemented
Assessment Rationale | Implement GtmStrategyAgent in backend, integrate GTM beachhead and channel selection skills, expose REST endpoints, and create GTM launchpad in frontend.
WORKBOOK TABLE OF CONTENTS
Sheet No. | Worksheet Name | Mandatory Section(s) Covered | Content Description
1 | INDEX & Executive Summary | Sections 1, 2, 12 | Executive Summary, Stage Overview, and Final Assessment
2 | QA Dashboard & Metrics | Section 10 | Test execution metrics, pass rates, requirement & defect coverage
3 | Capability Audit | Section 3 | Capability and requirement traceability matrix against product docs
4 | Agent & Workflow Tests | Sections 5, 6 | Agent-level verification, prompt pipeline, and workflow handoffs
5 | Test Execution and Evidence | Sections 4, 7, 9 | Detailed test procedures, negative/boundary tests, and evidence log
6 | Defect Register | Section 8 | Comprehensive defect register with severity, priority, and repro steps
7 | DEV Fix and Retest | Section 11 | Remediation plan, developer action tracker, and retest procedures

## QA Dashboard & Metrics
STAGE 06 — QA EXECUTION DASHBOARD & METRICS
Stage: Pre-Traction & GTM ¦ Target: QA Environment (https://qa.axiorapulse.com)
CATEGORY | METRIC NAME | VALUE | REMARKS / BASIS
Test Execution Metrics | Total Identified Test Cases | 5 | Formal test cases specified
Test Execution Metrics | Total Executed Test Cases | 5 | Cases executed against QA and codebase
Test Execution Metrics | Passed Test Cases | 1 | Acceptance criteria fully met with evidence
Test Execution Metrics | Failed Test Cases | 4 | Material defect or functional absence confirmed
Test Execution Metrics | Blocked Test Cases | 0 | Execution blocked by missing prerequisite/feature
Test Execution Metrics | Partial Test Cases | 0 | Partially functional / incomplete behavior
Test Execution Metrics | Untested Test Cases | 0 | Unexecuted scenarios
Test Execution Metrics | Executed Test Pass Rate | 20.0% | Passed / Executed Cases
Capability Coverage | Total Documented Capabilities | 8 | From Docs specification sheets
Capability Coverage | Implemented / Available Capabilities | 0 | Operational in codebase / QA
Capability Coverage | Capability Implementation Coverage | 0.0% | Implemented / Documented
Defect Summary | Critical (P1) Defects | 1 | Blocks stage execution / Missing core agent
Defect Summary | High (P2) Defects | 2 | Major feature failure or missing workflow API
Defect Summary | Medium (P3) Defects | 0 | Usability, navigation, or data presentation defect
Defect Summary | Low (P4) Defects | 0 | Minor cosmetic or text inconsistency

## Capability Audit
STAGE 06 — CAPABILITY & REQUIREMENT AUDIT MATRIX
Traceability matrix between product capability specifications in Docs/ and implementation in QA
Capability ID | Capability Name | Architectural Layer | Responsible Agent | Documented Expected Behaviour | Implementation Status | Actual QA Application Evidence | Audit Disposition
PTGTM.1 | Beachhead Segment & Early Adopter Definition | Layer 1 | GTM Strategy Agent | Isolate single highest-propensity beachhead customer segment for immediate focus | Documented but not implemented | Verified live: gtm_result is NULL in database. | Blocked
PTGTM.2 | Brand Positioning & Value Proposition Matrix | Layer 2 | GTM Strategy Agent | Define clear positioning statement, competitive differentiation, and tagline | Documented but not implemented | No calculation or generation engine exists. | Blocked
PTGTM.3 | Landing Page Structure & Copywriting Guidance | Layer 3 | GTM Strategy Agent | Generate high-converting landing page headline, hero copy, social proof, and CTA | Documented but not implemented | No generation engine exists. | Blocked
PTGTM.4 | Waitlist & Early-Access Lead Magnet Strategy | Layer 4 | GTM Strategy Agent | Design waitlist incentives, referral loops, and early-access onboarding flow | Documented but not implemented | No agent or backend service exists. | Blocked
PTGTM.5 | Community Building: WhatsApp & Discord Architecture | Layer 5 | GTM Strategy Agent | Formulate guidelines for community onboarding, engagement cadence, and founder AMA | Documented but not implemented | No agent exists. | Blocked
PTGTM.6 | Founder-Led Content & Thought Leadership Engine | Layer 6 | GTM Strategy Agent | Generate weekly LinkedIn/X content pillars around problem awareness and founder journey | Documented but not implemented | No agent exists. | Blocked
PTGTM.7 | Pre-Sales & Early Commitment Mechanism | Layer 7 | GTM Strategy Agent | Structure LOIs, paid pre-orders, refundable deposits, or design partner contracts | Documented but not implemented | No agent exists. | Blocked
PTGTM.8 | Launch Audience Readiness Audit & Score | Layer 8 | GTM Strategy Agent | Evaluate waitlist size, engagement rate, and community sentiment before launch | Documented but not implemented | No agent exists. | Blocked

## Agent & Workflow Tests
STAGE 06 — AGENT-LEVEL & WORKFLOW EVALUATION
Evaluation of agent availability, orchestration, prompt pipelines, and workflow state transitions
AGENT-LEVEL EVALUATION
Agent Name | Documented Responsibility | Doc Reference | Availability in Codebase | Test Inputs (AI Boss Context) | Expected Output Structure | Actual Observed Output | Verification Result | Defect / Architectural Finding
GTM Strategy Agent (app/agents/gtm_strategy_agent.py) | Beachhead customer selection, brand positioning, waitlist, founder content | Docs/V2 - PRE Traction & GTM.xlsx | Stub Placeholder (app/agents/gtm_strategy_agent.py) | AI Boss: Target tech startups with 10-50 employees struggling with remote async tracking | Positioning statement, waitlist referral mechanics, and content pillars | No output generated. Agent file is 2-line comment stub. | FAIL | S06-DEF-001: Agent is completely unimplemented in backend
Market Strategy Agent (Docs/Market Strategy Agent.xlsx) | Execute stage activities for Pre-Traction & GTM | Docs/Pre-Traction & GTM.xlsx | Not Implemented (Missing from app/agents/) | AI Boss: Stage 6 test scenario execution | Structured stage deliverable and Stage 7 prerequisite handoff | Zero backend agent file, zero API router, zero database execution logic. | BLOCKED | S06-DEF-001: Agent not implemented in backend
WORKFLOW & INTEGRATION EVALUATION
Workflow Scenario | Preconditions | Trigger / Action | Observed State Transition | Data Persistence Result | Integration Handoff Result | Status
Stage 06 Entry Gate Check | Stage 5 incomplete | Founder attempts to start Stage 6 | Stage remains Pending / Locked; directs founder to Stage 5 | Workspace state preserved in database | Upstream prerequisite enforcement confirmed | PASS
Stage 06 Execution Trigger | Stage 5 validated | Trigger Stage 06 action via API or UI | No API or UI trigger exists; operation rejected with 404 | Field remains NULL in database | Handoff to downstream stages blocked | FAIL
Stage 06 Data Integrity Across Reload | Workspace active in QA | Reload page or query state API | Workspace state reloaded cleanly without corruption | State perfectly persisted in PostgreSQL database | JWT session preserved | PASS

## Test Execution and Evidence
STAGE 06 — DETAILED TEST EXECUTION & EVIDENCE REGISTER
Full test scenario procedures, execution logs, expected vs actual results, and evidence links
Test Case ID | Test Category | Layer | Capability ID(s) | Test Objective / Scenario | Preconditions & Test Data | Detailed Execution Steps | Expected Result | Actual Result | Execution Status | Defect Reference | Evidence File Reference
S06-TC-001 | Architecture / Codebase | Layer 1-8 | PTGTM.1-PTGTM.8 | Inspect Backend GTM Strategy Agent Implementation | axiora-pulse-be codebase | Examine app/agents/gtm_strategy_agent.py | Complete agent class with skill integration and prompt pipeline | File contains only 2 lines: '# Reserved for Phase 2: GTM Strategy Agent.' | FAIL | S06-DEF-001 | app/agents/gtm_strategy_agent.py
S06-TC-002 | API Availability | Layer 1-8 | PTGTM.1-PTGTM.8 | Query Workspace GTM Endpoint | QA URL and auth token | GET https://qa.axiorapulse.com/api/v1/workspaces/424/gtm | 200 OK with GTM strategy object or 400 with prerequisites | HTTP 404 Not Found. | FAIL | S06-DEF-002 | API curl response
S06-TC-003 | UI / Journey Sidebar | Shared Platform | PTGTM.1 | Verify Stage 6 in Journey Sidebar | Workspace 424 open in QA | Click Step 6 'Pre-Traction & GTM' | Opens GTM strategy builder or waitlist dashboard | Static text drawer with bullet points. No actionable workflow. | FAIL | S06-DEF-003 | S06-EV-001_Journey_Stage_State.png
S06-TC-004 | Data Schema | Layer 1 | PTGTM.1 | Verify Database Column for GTM Results | axiora-pulse-be models | Check Workspace model in app/db/models.py | gtm_result JSON column exists | Column exists: gtm_result = Column(JSON, nullable=True). Evaluates to NULL in QA. | PASS |  | app/db/models.py:231
S06-TC-005 | Live Output Validation | Layer 1-8 | PTGTM.1 | Validate Stage 6 Output Presence Post-Validation | Workspace 424 state API | GET /api/v1/workspaces/424/state -> gtm_result | GTM strategy output populated | gtm_result is None. Confirms zero Stage 6 output generation. | FAIL | S06-DEF-001 | Workspace 424 state JSON

## Defect Register
STAGE 06 — DEFECT REGISTER
Recorded defects, severity classification, reproduction steps, evidence, and remediation
Defect ID | Module / Area | Capability Reference | Defect Title | Defect Category | Severity | Priority | Preconditions | Reproduction Steps | Expected Result | Actual Result | Evidence Reference | Recommended Remediation | Retest Status
S06-DEF-001 | Backend Agent | PTGTM.1-PTGTM.8 | GTM Strategy Agent is an Unimplemented Stub in Backend | Architecture / Backend | Critical | P1 | axiora-pulse-be repository | Inspect app/agents/gtm_strategy_agent.py | Agent should inherit from BaseAgent and implement GTM positioning logic. | File is an empty placeholder containing only a comment. | app/agents/gtm_strategy_agent.py | Implement GtmStrategyAgent with beachhead and messaging skills, register in AGENT_REGISTRY. | Open
S06-DEF-002 | API Endpoint | PTGTM.1-PTGTM.8 | Missing /workspaces/{id}/gtm Endpoint | API / Routing | High | P1 | FastAPI router | GET /api/v1/workspaces/424/gtm | Returns GTM strategy and waitlist analytics. | Returns HTTP 404 Not Found. | API curl response | Implement router app/api/v1/gtm.py. | Open
S06-DEF-003 | Frontend UI | PTGTM.1-PTGTM.8 | No Interactive GTM or Waitlist Management UI | UI / UX | High | P2 | Workspace view in QA | Click Step 6 in Journey card | Opens GTM campaign and positioning builder. | Static text drawer only. | S06-EV-001_Journey_Stage_State.png | Build GtmStrategyPage in frontend. | Open

## DEV Fix and Retest
STAGE 06 — REMEDIATION & RETEST TRACKER
Action items, developer ownership, priority, retest procedures, and exit gates
Action ID | Source Type | Defect Reference | Capability IDs | Action Title | Required DEV Action | Priority | DEV Owner | DEV Status | Retest Procedure | Exit Gate
ACT-Stage_06-001 | Confirmed Defect | S06-DEF-001 | PTGTM.1-PTGTM.8 | GTM Strategy Agent is an Unimplemented Stub in Backend | Implement GtmStrategyAgent with beachhead and messaging skills, register in AGENT_REGISTRY. | P1 | Backend / AI Team | TODO - Fix Required | Execute S06-DEF-001 reproduction steps in QA environment after build deployment. | Passing automated test and verified evidence in Stage 06 report.
ACT-Stage_06-002 | Confirmed Defect | S06-DEF-002 | PTGTM.1-PTGTM.8 | Missing /workspaces/{id}/gtm Endpoint | Implement router app/api/v1/gtm.py. | P1 | Frontend / UI Team | TODO - Fix Required | Execute S06-DEF-002 reproduction steps in QA environment after build deployment. | Passing automated test and verified evidence in Stage 06 report.
ACT-Stage_06-003 | Confirmed Defect | S06-DEF-003 | PTGTM.1-PTGTM.8 | No Interactive GTM or Waitlist Management UI | Build GtmStrategyPage in frontend. | P2 | Frontend / UI Team | TODO - Fix Required | Execute S06-DEF-003 reproduction steps in QA environment after build deployment. | Passing automated test and verified evidence in Stage 06 report.