## INDEX & Executive Summary
AXIORA PULSE — QUALITY ASSURANCE & AUDIT REPORT
Stage 07: Testing, Pilot & Improvement ¦ Reference Concept: AI Boss (Autonomous Organizational Platform)
METADATA ATTRIBUTE | DETAILS / SPECIFICATION
Official Stage ID | Stage_07
Official Stage Name | Testing, Pilot & Improvement
Execution Date | 2026-10-22
QA Target URL | https://qa.axiorapulse.com/login
Test Execution Lead | Antigravity Autonomous QA Lead & Evaluation Agent
Active QA Account | ntortj@gmail.com
Target Workspace | Workspace ID: 424 ('Idea') / Workspace ID: 416 ('AI mentor')
Evaluated Application | AI Boss (Autonomous Organizational Management & Coordination Engine)
Overall Stage Status | BLOCKED — NOT IMPLEMENTED (LIVE VERIFIED)
Final Stage Assessment | Not Validated — Documented but Not Implemented
SECTION 1 — EXECUTIVE SUMMARY
Testing Scope & Mandate | Comprehensive functional, agent-level, architectural, and workflow evaluation of Stage 07 (Testing, Pilot & Improvement) against authoritative product specifications, local codebase, and the live QA environment.
Key Findings | Stage 7 output was verified live in Workspace 424. The test_pilot_result column in the database evaluates to NULL. There is no backend agent, no API router (/api/v1/workspaces/424/pilot returns 404), and no frontend UAT/pilot interface.
Critical Blockers | 1. No backend agent in app/agents/ for testing or pilot governance. 2. API route /api/v1/workspaces/{id}/pilot returns 404. 3. Frontend has no UAT checklist, bug tracker, or Launch Readiness dashboard. 4. Stage 7 in Journey card is an un-interactive informational drawer.
Progression Recommendation | Stage 07 cannot be signed off for general release. Address critical defects and implement the missing agent/API/UI layer before opening this stage in the user journey.
SECTION 2 — STAGE OVERVIEW & LIFECYCLE CONTEXT
Business Objective | QA, user acceptance testing (UAT), beta pilot cohort recruitment, product/service quality testing, usability testing, early customer feedback, bug triage, and Launch Readiness Score and verdict.
Entry Criteria | Completion of Stage 6 with verified status and approval gate passed.
Exit Criteria | Validated Stage 07 artifacts, approved stage verdict, and prerequisite handoff data published.
Relevant Agents | Testing, Pilot & Improvement Agent (Docs/Testing, Pilot & Improvement (1).xlsx)
Upstream Dependencies | Stage 6 deliverables and Strategic Memory state.
Downstream Handoffs | Stage 8 input context and audit traces.
SECTION 12 — FINAL STAGE READINESS ASSESSMENT
Final Disposition | Not Validated — Documented but Not Implemented
Assessment Rationale | Implement TestingPilotAgent in backend, build Launch Readiness Scoring engine, expose REST endpoints, and create Pilot Feedback dashboard in frontend.
WORKBOOK TABLE OF CONTENTS
Sheet No. | Worksheet Name | Mandatory Section(s) Covered | Content Description
1 | INDEX & Executive Summary | Sections 1, 2, 12 | Executive Summary, Stage Overview, and Final Assessment
2 | QA Dashboard & Metrics | Section 10 | Test execution metrics, pass rates, requirement & defect coverage
3 | Capability Audit | Section 3 | Capability and requirement traceability matrix against product docs
4 | Agent & Workflow Tests | Sections 5, 6 | Agent-level verification, prompt pipeline, and workflow handoffs
5 | Test Execution and Evidence | Sections 4, 7, 9 | Detailed test procedures, negative/boundary tests, and evidence log
6 | Defect Register | Section 8 | Comprehensive defect register with severity, priority, and repro steps
7 | DEV Fix and Retest | Section 11 | Remediation plan, developer action tracker, and retest procedures

## QA Dashboard & Metrics
STAGE 07 — QA EXECUTION DASHBOARD & METRICS
Stage: Testing, Pilot & Improvement ¦ Target: QA Environment (https://qa.axiorapulse.com)
CATEGORY | METRIC NAME | VALUE | REMARKS / BASIS
Test Execution Metrics | Total Identified Test Cases | 5 | Formal test cases specified
Test Execution Metrics | Total Executed Test Cases | 5 | Cases executed against QA and codebase
Test Execution Metrics | Passed Test Cases | 1 | Acceptance criteria fully met with evidence
Test Execution Metrics | Failed Test Cases | 4 | Material defect or functional absence confirmed
Test Execution Metrics | Blocked Test Cases | 0 | Execution blocked by missing prerequisite/feature
Test Execution Metrics | Partial Test Cases | 0 | Partially functional / incomplete behavior
Test Execution Metrics | Untested Test Cases | 0 | Unexecuted scenarios
Test Execution Metrics | Executed Test Pass Rate | 20.0% | Passed / Executed Cases
Capability Coverage | Total Documented Capabilities | 8 | From Docs specification sheets
Capability Coverage | Implemented / Available Capabilities | 0 | Operational in codebase / QA
Capability Coverage | Capability Implementation Coverage | 0.0% | Implemented / Documented
Defect Summary | Critical (P1) Defects | 1 | Blocks stage execution / Missing core agent
Defect Summary | High (P2) Defects | 2 | Major feature failure or missing workflow API
Defect Summary | Medium (P3) Defects | 0 | Usability, navigation, or data presentation defect
Defect Summary | Low (P4) Defects | 0 | Minor cosmetic or text inconsistency

## Capability Audit
STAGE 07 — CAPABILITY & REQUIREMENT AUDIT MATRIX
Traceability matrix between product capability specifications in Docs/ and implementation in QA
Capability ID | Capability Name | Architectural Layer | Responsible Agent | Documented Expected Behaviour | Implementation Status | Actual QA Application Evidence | Audit Disposition
TPI.1 | Pilot Cohort Definition & Participant Selection | Layer 1 | Testing & Pilot Agent | Define beta cohort size (10-30 users), eligibility criteria, and onboarding playbook | Documented but not implemented | Verified live: test_pilot_result is NULL in database. | Blocked
TPI.2 | UAT Checklist & Quality Standard Verification | Layer 2 | Testing & Pilot Agent | Provide structured test scripts covering core user journeys and edge cases | Documented but not implemented | No service exists. | Blocked
TPI.3 | Product Usability & Task Completion Tracking | Layer 3 | Testing & Pilot Agent | Measure task completion rate, drop-off steps, and usability friction points | Documented but not implemented | No service exists. | Blocked
TPI.4 | Pilot Customer Qualitative Feedback Loop | Layer 4 | Testing & Pilot Agent | Collect structured feedback on product value, feature gaps, and confusion | Documented but not implemented | No service exists. | Blocked
TPI.5 | Bug & Issue Severity Triage Engine | Layer 5 | Testing & Pilot Agent | Classify reported bugs by severity (Critical, High, Medium, Low) and release impact | Documented but not implemented | No service exists. | Blocked
TPI.6 | Pricing & Value Perception Feedback Analysis | Layer 6 | Testing & Pilot Agent | Capture pilot participants' willingness to pay once the free beta ends | Documented but not implemented | No service exists. | Blocked
TPI.7 | Launch Readiness Score (0-100) & Gate Decision | Layer 7 | Launch Readiness Engine | Calculate algorithmic readiness score based on bug count, feedback, and stability | Documented but not implemented | No service exists. | Blocked
TPI.8 | Go / No-Go / Extended-Pilot Verdict Governance | Layer 8 | Launch Readiness Engine | Issue authoritative launch verdict (Proceed to Commercial Launch / Extended Pilot / Fix Blockers) | Documented but not implemented | No service exists. | Blocked

## Agent & Workflow Tests
STAGE 07 — AGENT-LEVEL & WORKFLOW EVALUATION
Evaluation of agent availability, orchestration, prompt pipelines, and workflow state transitions
AGENT-LEVEL EVALUATION
Agent Name | Documented Responsibility | Doc Reference | Availability in Codebase | Test Inputs (AI Boss Context) | Expected Output Structure | Actual Observed Output | Verification Result | Defect / Architectural Finding
Testing, Pilot & Improvement Agent (Docs/Testing, Pilot & Improvement (1).xlsx) | Execute stage activities for Testing, Pilot & Improvement | Docs/Testing, Pilot & Improvement.xlsx | Not Implemented (Missing from app/agents/) | AI Boss: Stage 7 test scenario execution | Structured stage deliverable and Stage 8 prerequisite handoff | Zero backend agent file, zero API router, zero database execution logic. | BLOCKED | S07-DEF-001: Agent not implemented in backend
WORKFLOW & INTEGRATION EVALUATION
Workflow Scenario | Preconditions | Trigger / Action | Observed State Transition | Data Persistence Result | Integration Handoff Result | Status
Stage 07 Entry Gate Check | Stage 6 incomplete | Founder attempts to start Stage 7 | Stage remains Pending / Locked; directs founder to Stage 6 | Workspace state preserved in database | Upstream prerequisite enforcement confirmed | PASS
Stage 07 Execution Trigger | Stage 6 validated | Trigger Stage 07 action via API or UI | No API or UI trigger exists; operation rejected with 404 | Field remains NULL in database | Handoff to downstream stages blocked | FAIL
Stage 07 Data Integrity Across Reload | Workspace active in QA | Reload page or query state API | Workspace state reloaded cleanly without corruption | State perfectly persisted in PostgreSQL database | JWT session preserved | PASS

## Test Execution and Evidence
STAGE 07 — DETAILED TEST EXECUTION & EVIDENCE REGISTER
Full test scenario procedures, execution logs, expected vs actual results, and evidence links
Test Case ID | Test Category | Layer | Capability ID(s) | Test Objective / Scenario | Preconditions & Test Data | Detailed Execution Steps | Expected Result | Actual Result | Execution Status | Defect Reference | Evidence File Reference
S07-TC-001 | Architecture / Codebase | Layer 1-8 | TPI.1-TPI.8 | Verify Backend Testing & Pilot Agent Presence | axiora-pulse-be codebase | Search app/agents/ for testing_pilot_agent.py | Agent present and registered in AGENT_REGISTRY | No agent exists for Stage 7 in backend. | FAIL | S07-DEF-001 | app/agents/ directory listing
S07-TC-002 | API Availability | Layer 1-8 | TPI.1-TPI.8 | Query Workspace Pilot Endpoint | QA URL and auth token | GET https://qa.axiorapulse.com/api/v1/workspaces/424/pilot | 200 OK with pilot scorecard or 400 with prerequisites | HTTP 404 Not Found. | FAIL | S07-DEF-002 | API curl response
S07-TC-003 | UI / Journey Sidebar | Shared Platform | TPI.1 | Verify Stage 7 in Journey Sidebar | Workspace 424 open in QA | Click Step 7 'Testing, Pilot & Improvement' | Opens pilot tracking dashboard and bug triage view | Static text drawer with bullet points. No actionable workflow. | FAIL | S07-DEF-003 | S07-EV-001_Journey_Stage_State.png
S07-TC-004 | Data Schema | Layer 1 | TPI.1 | Verify Database Column for Pilot Results | axiora-pulse-be models | Check Workspace model in app/db/models.py | test_pilot_result JSON column exists | Column exists: test_pilot_result = Column(JSON, nullable=True). Evaluates to NULL in QA. | PASS |  | app/db/models.py:232
S07-TC-005 | Live Output Validation | Layer 1-8 | TPI.1 | Validate Stage 7 Output Presence Post-Validation | Workspace 424 state API | GET /api/v1/workspaces/424/state -> test_pilot_result | Launch readiness scorecard populated | test_pilot_result is None. Confirms zero Stage 7 output generation. | FAIL | S07-DEF-001 | Workspace 424 state JSON

## Defect Register
STAGE 07 — DEFECT REGISTER
Recorded defects, severity classification, reproduction steps, evidence, and remediation
Defect ID | Module / Area | Capability Reference | Defect Title | Defect Category | Severity | Priority | Preconditions | Reproduction Steps | Expected Result | Actual Result | Evidence Reference | Recommended Remediation | Retest Status
S07-DEF-001 | Backend Agent | TPI.1-TPI.8 | Testing, Pilot & Improvement Agent Missing from Backend | Architecture / Backend | Critical | P1 | axiora-pulse-be repository | Inspect app/agents/ | TestingPilotAgent should exist and compute Launch Readiness Score. | No agent file exists. | app/agents/ directory listing | Implement TestingPilotAgent and register in AGENT_REGISTRY. | Open
S07-DEF-002 | API Endpoint | TPI.1-TPI.8 | Missing /workspaces/{id}/pilot Endpoint | API / Routing | High | P1 | FastAPI router | GET /api/v1/workspaces/424/pilot | Returns pilot metrics, feedback summary, and launch readiness score. | Returns HTTP 404 Not Found. | API curl response | Create router app/api/v1/pilot.py. | Open
S07-DEF-003 | Frontend UI | TPI.1-TPI.8 | No Pilot Governance or Launch Readiness Dashboard | UI / UX | High | P2 | Workspace view in QA | Click Step 7 in Journey card | Display beta cohort tracking and Launch Readiness Score gauge. | Static text only. | S07-EV-001_Journey_Stage_State.png | Build TestingPilotPage in frontend. | Open

## DEV Fix and Retest
STAGE 07 — REMEDIATION & RETEST TRACKER
Action items, developer ownership, priority, retest procedures, and exit gates
Action ID | Source Type | Defect Reference | Capability IDs | Action Title | Required DEV Action | Priority | DEV Owner | DEV Status | Retest Procedure | Exit Gate
ACT-Stage_07-001 | Confirmed Defect | S07-DEF-001 | TPI.1-TPI.8 | Testing, Pilot & Improvement Agent Missing from Backend | Implement TestingPilotAgent and register in AGENT_REGISTRY. | P1 | Backend / AI Team | TODO - Fix Required | Execute S07-DEF-001 reproduction steps in QA environment after build deployment. | Passing automated test and verified evidence in Stage 07 report.
ACT-Stage_07-002 | Confirmed Defect | S07-DEF-002 | TPI.1-TPI.8 | Missing /workspaces/{id}/pilot Endpoint | Create router app/api/v1/pilot.py. | P1 | Frontend / UI Team | TODO - Fix Required | Execute S07-DEF-002 reproduction steps in QA environment after build deployment. | Passing automated test and verified evidence in Stage 07 report.
ACT-Stage_07-003 | Confirmed Defect | S07-DEF-003 | TPI.1-TPI.8 | No Pilot Governance or Launch Readiness Dashboard | Build TestingPilotPage in frontend. | P2 | Frontend / UI Team | TODO - Fix Required | Execute S07-DEF-003 reproduction steps in QA environment after build deployment. | Passing automated test and verified evidence in Stage 07 report.