## Context, Entry and Outcome
Seq | Layer | Capability ID | Capability Name | Purpose | Trigger | Inputs | Processing | Outputs | Consumed By | Business Rules | Success Criteria | Future Scope
1 | Layer 1 - Context, Entry & Outcome Foundation | MEP.1 | Agent Initialization & Cross-Stage Intelligence Handoff | Start Stage 4 with the latest validated intelligence from Idea Validation, Market Research/Business Model and Financial & Capital Planning rather than re-interrogating the founder. | Stage 4 starts or a material upstream output is updated. | Stage 1 problem/customer/validation outputs; Stage 2 ICP, pricing, revenue and demand evidence; Stage 3 capital envelope, runway, resource budgets and financial-readiness outputs; user uploads. | Load versioned upstream context, identify source/confidence/date, detect missing or stale prerequisites and create one execution-planning context. | Stage 4 execution context; inherited evidence register; missing/stale-input list. | MEP.2–MEP.10, MEP.88–MEP.89 | Do not silently replace upstream decisions. Reuse existing information unless a clarification materially changes scope, risk, capital or feasibility. | The agent starts with traceable Stage 1–3 context and does not ask the founder to repeat known information. | Automated cross-agent dependency/version graph.
2 | Layer 1 - Context, Entry & Outcome Foundation | MEP.2 | Entry Eligibility & Prerequisite Gate | Determine whether Stage 4 can responsibly proceed to scoping or must return to an earlier stage. | Stage 4 initialization or a prerequisite becomes low-confidence/contradictory. | Validated problem; primary customer/ICP; value proposition; validation confidence; business model; Stage-3 capital envelope; critical legal/regulatory blockers. | Check minimum entry conditions and classify each prerequisite as pass, conditional, missing or blocking. | Entry status; blocking gaps; return-to-stage recommendation. | MEP.3–MEP.10, MEP.79, MEP.86 | Do not create a confident MVP plan when problem/customer/value is unclear, capital envelope is missing, or a mandatory blocker is unresolved. | No detailed scope/roadmap is generated while a blocking prerequisite remains unresolved. | Configurable entry rules by lifecycle stage and business type.
3 | Layer 1 - Context, Entry & Outcome Foundation | MEP.3 | Progressive Intake & High-Value Clarification | Collect only the additional information that materially changes scope, feasibility, cost, quality, timeline or evidence design. | Missing or ambiguous Stage 4 inputs are detected. | Execution context; proposed scope; team/capability data; deadlines; technology/data dependencies; quality/compliance requirements; evidence expectations; business-type conditional inputs (e.g. AI/model/data constraints, BOM/MOQ/certification, F&B licences/kitchen/packaging, marketplace liquidity/trust, service capacity/SOPs, B2B procurement/security/SLA). | Prioritize clarifying questions by decision impact; activate the relevant conditional intake pack by business type; ask only questions that can change scope, feasibility, cost, quality, timeline, risk or evidence design; stop asking when sufficient evidence exists for the next decision. | Prioritized clarification list; completed Stage 4 intake; business-type conditional-input record; unresolved unknowns. | MEP.4–MEP.16 | Questions must be decision-relevant; avoid long generic questionnaires and do not fabricate missing facts. Conditional input packs must be applied only when relevant to the founder's business type. | All mandatory and business-type-specific decision inputs are known or explicitly labelled unknown before strong recommendations are produced. | Adaptive question ordering learned from prior founder patterns.
4 | Layer 1 - Context, Entry & Outcome Foundation | MEP.4 | Founder & Business Execution Context | Create the Stage 4 operating context that shapes scope and execution choices. | Initialization or material business-model/geography/stage change. | Business type; industry; geography; B2B/B2C/B2B2C/B2G; delivery model; pricing/revenue model; current stage; founder experience; founder risk appetite; maximum acceptable loss from Stage 3 where available; existing systems, suppliers, locations and constraints. | Normalize business and founder execution context; identify execution characteristics and risk boundaries that affect MVP shape, compliance, operations, delivery mode and irreversible commitments. | Execution-context profile; founder risk-boundary context; business-type flags; context constraints. | MEP.5–MEP.45 | Execution guidance must be context-sensitive; do not force a SaaS template onto service, physical-product, F&B, marketplace or enterprise businesses. Founder risk appetite never overrides protected reserves, mandatory quality, legal/compliance or other hard gates. | Every scope and feasibility recommendation cites the relevant business/founder context and respects the stated risk boundary. | Additional sector-specific context packs.
5 | Layer 1 - Context, Entry & Outcome Foundation | MEP.5 | Founder Capacity & Bandwidth Adaptation | Fit the plan to the founder's realistic time, oversight capacity and available team rather than an assumed full-time founder. | Founder availability/team composition is known or changes. | Full-time/side-hustle status; co-founders; existing team; founder skills/experience; oversight capacity; founder risk appetite; maximum acceptable loss; hard personal/business constraints. | Classify founder mode and adjust scope, parallel workstreams, cadence, build approach and timeline assumptions; use experience/risk appetite only to choose between otherwise viable/reversible approaches, never to relax capital, quality or compliance gates. | Founder-capacity profile; experience/risk profile; cadence adjustment; scope/oversight constraints. | MEP.35, MEP.37, MEP.53–MEP.56, MEP.63–MEP.73 | Side-hustle/solo founders require more conservative sequencing; parallel workstreams are allowed only when real ownership capacity exists. Risk appetite is a planning input, not permission to expose protected survival capital. | Timeline, build approach and resource plan can be executed with the founder's actual availability, experience and acceptable-risk boundary. | Calendar-linked capacity planning.
6 | Layer 1 — Context, Entry & Outcome Foundation | MEP.6 | Full-Scope Dream Capture | Preserve the founder's complete vision before reduction so cuts are transparent rather than silently imposed. | Founder describes the desired product/service or supplies an existing feature list. | Founder narrative; sketches/docs; stakeholder asks; existing roadmap; proposed features/services/geographies/channels. | Capture the full vision in the founder's own terms and extract its discrete scope elements without prioritizing yet. | Full-scope vision statement; initial scope universe. | MEP.7, MEP.18 | Do not prematurely cut or rewrite the founder's vision during capture; separate capture from prioritization. | The founder can see the complete dream version that later scope decisions are compared against. | Multimodal scope extraction from whiteboards/prototypes.
7 | Layer 1 — Context, Entry & Outcome Foundation | MEP.7 | Dream-vs-Reality Gap Mapping | Make the mismatch between the full vision and current capital, time, evidence and resource reality visible. | Full-scope vision exists and Stage-3 capital/context is available. | Full-scope vision; directional effort/cost evidence; capital ceiling; founder capacity; critical uncertainties. | Compare the full vision with current constraints and identify the largest scope, cost, time and evidence gaps. | Reality-gap statement; gap drivers; reduction requirement. | MEP.15, MEP.18–MEP.29, MEP.63 | Directional estimates must be labelled; do not present unsupported multipliers as fact for a specific founder. | Founder understands why the full vision cannot/should not be the first build where constraints do not support it. | Scenario comparison of multiple reduced-scope options.
8 | Layer 1 — Context, Entry & Outcome Foundation | MEP.8 | Customer / User / Buyer / Payer / Approver Context | Define who receives value, who uses, pays, approves or benefits so MVP scope is anchored to the correct decision-maker and workflow. | Before core outcome and feature prioritization. | Primary customer; user; buyer; payer; approver; beneficiary; beachhead segment; B2B decision-maker/procurement context. | Resolve role distinctions and choose the one primary Version-1 customer while retaining other commercial roles. | Primary customer role map; beachhead user/buyer context. | MEP.9–MEP.27, MEP.46 | One primary Version-1 customer must anchor the MVP; multiple unrelated customer segments require scope reduction or separate future phases. | The MVP can be described for one clear customer and buying/use context. | Multi-stakeholder enterprise journey models.
9 | Layer 1 — Context, Entry & Outcome Foundation | MEP.9 | Core Problem & Measurable Customer Outcome | Translate validated pain into one explicit problem and measurable customer result that Version 1 must deliver. | Entry conditions pass and the primary customer is clear. | Validated pain; root cause; current workaround; desired outcome; customer evidence; commercial evidence. | Create a concise problem statement and outcome using customer, context, job/result and measurable completion/improvement criteria. | Signed-off core problem; measurable customer outcome. | MEP.10–MEP.34, MEP.46, MEP.74 | Customer outcome comes before features. Do not use Stage 4 execution planning to compensate for a weak or invalidated problem. | The founder can explain the one core problem and one customer outcome in plain language. | Outcome benchmark libraries by use case.

## Assumption and 1st Bet Strategy
Seq | Layer | Capability ID | Capability Name | Purpose | Trigger | Inputs | Processing | Outputs | Consumed By | Business Rules | Success Criteria | Future Scope
10 | Layer 2 — Assumption & First-Bet Strategy | MEP.10 | MVP Thesis & Evidence Goal | State what the first version is expected to deliver and what evidence would justify the next investment. | Core problem/outcome is approved. | Primary customer; core problem/outcome; value proposition; commercial evidence; Stage-3 constraints. | Form an MVP thesis linking capability, customer, context, intended outcome and behavioural/commercial evidence. | MVP thesis; primary evidence goal; next-investment question. | MEP.11–MEP.16, MEP.74 | A roadmap is not the outcome; the thesis must identify what the business needs to learn or prove. | MVP thesis is specific enough to be tested and tied to a next decision. | Multiple hypothesis portfolio for complex ventures.
11 | Layer 2 — Assumption & First-Bet Strategy | MEP.11 | Material Assumption Register | Make the assumptions that justify spending explicit across customer, value, technical, operational, cost, resource, channel and compliance areas. | MVP thesis is defined or a new material unknown appears. | Founder beliefs; upstream assumptions; technical/operational unknowns; cost/resource assumptions; compliance and channel assumptions. | Capture each assumption with evidence today, impact if wrong, confidence and source. | Versioned assumption register. | MEP.12–MEP.16, MEP.74, MEP.88 | Assumptions are not facts. Each material assumption must be labelled and traceable to evidence or uncertainty. | High-impact unproven beliefs are visible before expensive work is planned. | Automated assumption aging and evidence refresh.
12 | Layer 2 — Assumption & First-Bet Strategy | MEP.12 | Assumption Impact–Uncertainty Prioritisation | Sequence learning around the assumptions most capable of invalidating the plan. | Assumption register contains multiple unknowns. | Assumptions; business impact; uncertainty/confidence; estimated test cost/time. | Rank assumptions by combined impact and uncertainty, with preference for cheap, reversible tests. | Ranked assumption backlog; top-risk assumption set. | MEP.13–MEP.16, MEP.74 | The most dangerous uncertain assumption is addressed before low-risk feature work; avoid expensive certainty where a cheap test can answer the same question. | Highest-risk uncertainties are clearly prioritized before build sequencing. | Probabilistic assumption portfolio scoring.
13 | Layer 2 — Assumption & First-Bet Strategy | MEP.13 | Fatal Assumption Detection | Identify the one or few unproven assumptions that could make the proposed build wasteful or non-viable. | Assumptions are ranked or a high-cost build is proposed. | Ranked assumptions; capital exposure; dependency chain; customer/technical/compliance evidence. | Flag assumptions whose failure invalidates core value, feasibility, legality, delivery or economics. | Fatal-assumption flag; reason; spend restriction. | MEP.14–MEP.16, MEP.74–MEP.76 | A critical technical or business assumption cannot remain untested while significant irreversible spend is recommended. | Every high-cost plan has a clearly tested or explicitly gated fatal assumption. | Automated kill-chain reasoning across linked assumptions.
14 | Layer 2 — Assumption & First-Bet Strategy | MEP.14 | Assumption Test & Evidence Threshold Design | Define the cheapest credible test, success threshold and failure decision for each material assumption. | A material/fatal assumption is selected for testing. | Assumption; available evidence; test channels; customer access; technical resources; budget/time ceiling. | Choose test method (research, prototype, POC, manual service, pre-sale, sample batch etc.), specify threshold, duration, data source and decision if passed/failed. | Assumption-test plan; success threshold; failure/next decision. | MEP.15–MEP.17, MEP.76 | Tests must unlock a decision; thresholds cannot be invented without rationale and should be founder-/context-specific. | Each material assumption has an actionable evidence test tied to a decision. | Experiment library with reusable templates.
15 | Layer 2 — Assumption & First-Bet Strategy | MEP.15 | First-Bet Type Decision Engine | Select whether the next step should be a POC, prototype, manual/concierge proof, MVP, or pilot-readiness preparation based on what is still uncertain. | Core outcome and top assumptions are known. | Dominant uncertainty; business type; customer access; technical/operational feasibility; automation cost; quality/compliance needs. | Apply decision rules to choose the lowest-cost form that can resolve the dominant uncertainty without overbuilding. | First-bet type; rationale; prerequisites. | MEP.16–MEP.17, MEP.80 | POC, prototype, manual proof and MVP are not interchangeable. Formal pilot execution belongs downstream; Stage 4 prepares for it. | Chosen first-bet format directly matches the dominant uncertainty and evidence goal. | Hybrid first-bet sequencing for multi-risk ventures.
16 | Layer 2 — Assumption & First-Bet Strategy | MEP.16 | First-Bet Scope & Proof Definition | Turn the selected first-bet type into a bounded scope explicitly designed to answer the target question. | First-bet type is chosen. | Selected format; fatal assumption; core outcome; available customer/sample/data; cost/time ceiling. | Define included proof elements, excluded product elements, test window, users/sample, success/failure thresholds and required evidence. | POC/prototype/manual/MVP proof scope; bounded test plan. | MEP.17, MEP.25, MEP.76 | A POC is a targeted experiment, not a smaller full product; manual proof is valid where it safely delivers the outcome at low volume. | The first bet can be executed in a bounded way and produces evidence for a named decision. | Template-specific proof canvases by industry.
17 | Layer 2 — Assumption & First-Bet Strategy | MEP.17 | MVP Core Loop & First-Bet Decision Gate | Define the smallest end-to-end value loop and the conditions that allow continuation, redesign, reduction or stop. | First-bet scope is being finalized. | Customer trigger; input; processing/service; value output; customer action/outcome; feedback/evidence; thresholds. | Map the core loop and attach success, failure and next-decision logic. | MVP core loop; success gate; failure gate; next-decision rule. | MEP.18–MEP.38, MEP.76, MEP.80 | If the core loop cannot be explained clearly, scope is not ready for execution. Completion of build work alone is not a pass. | The team can explain the complete value loop and what evidence unlocks the next investment. | Journey instrumentation templates linked to the core loop.

## Feature Intelligence and Scope
Seq | Layer | Capability ID | Capability Name | Purpose | Trigger | Inputs | Processing | Outputs | Consumed By | Business Rules | Success Criteria | Future Scope
18 | Layer 3 — Feature Intelligence & Scope Architecture | MEP.18 | Feature Universe Builder | Create a complete, clean list of all requested or implied capabilities before prioritisation. | Full-scope vision, stakeholder inputs or existing feature lists are available. | Founder vision; customer requests; competitor/substitute insights; operational needs; technical/compliance requirements. | Extract discrete features, ask targeted questions for implied capabilities, merge near-duplicates and flag ambiguities for confirmation. | Clean feature universe with source and ambiguity status. | MEP.19–MEP.29 | Nothing should be cut before it is named; duplicate features must not inflate scope. | All known scope elements are represented once with clear meaning before scoring. | Automated semantic duplicate detection across uploads/backlogs.
19 | Layer 3 — Feature Intelligence & Scope Architecture | MEP.19 | Pain → Problem → Outcome → Feature Traceability | Ensure every proposed MVP capability has a defensible link to validated customer value. | Feature universe exists. | Feature items; validated pains/root causes; core problem; target outcome; evidence sources. | Create traceability links from pain/root cause to problem, outcome, feature and evidence. | Feature traceability matrix. | MEP.20–MEP.29, MEP.49 | Features driven only by internal preference are not automatically eligible for MVP. | Every included feature can be traced to a validated outcome or mandatory risk/evidence need. | Bidirectional traceability into backlog and testing tools.
20 | Layer 3 — Feature Intelligence & Scope Architecture | MEP.20 | Feature Justification Gate | Block features that do not directly enable core value, mandatory trust/compliance or critical evidence. | A feature is considered for MVP. | Feature traceability; quality/security/compliance needs; evidence plan. | Evaluate whether the feature meets at least one valid inclusion justification. | Justification status; inclusion rationale; postpone/remove candidate. | MEP.21–MEP.29 | Valid justifications are: core customer outcome, mandatory safety/security/compliance/reliability, or critical evidence generation. | No MVP feature remains without a documented inclusion reason. | Policy rules for regulated feature categories.
21 | Layer 3 — Feature Intelligence & Scope Architecture | MEP.21 | Feature Classification & Priority Taxonomy | Classify scope using compatible business-value and execution-priority views without duplicating features. | Feature universe is justified and traceable. | Feature item; customer value; differentiation; necessity; evidence; risk; timing. | Assign Core/Differentiator/Nice-to-have/Vanity and execution priority P0/P1/P2/P3; map to MoSCoW where required. | Multi-axis feature classification; MoSCoW/P0 mapping. | MEP.22–MEP.29, MEP.78 | Classification axes are complementary, not separate copies of the feature. A feature cannot be Core without validated value or a mandatory requirement. | Founders and builders see one feature list with consistent priority semantics. | Configurable taxonomy views for different delivery partners.
22 | Layer 3 — Feature Intelligence & Scope Architecture | MEP.22 | Weighted Feature Scoring | Rank features using the CEO-defined 100-point default model across problem alignment, customer value, evidence, commercial value, necessity, trust/quality, effort and timing. | Features are classified. | Core-problem alignment; customer value; evidence value; commercial value; necessity; quality/compliance; effort/cost; technical/operational risk; timing. | Apply the default weights: Core Problem 15, Customer 15, Evidence 10, Commercial 10, Necessity 10, Quality/Compliance 10, Effort/Cost 10, Technical/Operational 10, Timing 10. Expose component scores and permit only governed/versioned policy changes. | Transparent 100-point feature score; component scores; ranked feature list. | MEP.23–MEP.29 | The listed weights are the CEO Detailed Specification default. Scoring cannot override hard safety/compliance needs, critical dependencies, evidence gates or capital constraints. Any future weight change requires explicit Product/CEO governance and versioning. | Feature rankings are reproducible from the CEO-default factors/weights and explainable from supporting evidence. | Business-type-specific scoring profiles only after governed validation.
23 | Layer 3 — Feature Intelligence & Scope Architecture | MEP.23 | Value vs Effort Sequencing Matrix | Separate quick wins, big bets, fill-ins and time sinks to sequence work inside the accepted scope. | Priority scores and directional effort are available. | Feature value score; effort estimate; dependency/uncertainty. | Plot/label high-low value and effort; identify quick wins, big bets, fill-ins and time sinks. | Impact/effort matrix; sequencing recommendation. | MEP.24–MEP.29, MEP.59, MEP.63 | Low-value/high-effort work is removed from MVP; high-value/high-effort work must be decomposed or proof-tested where possible. | Build sequence maximizes learning/value per unit of scarce effort. | Portfolio optimization across multiple MVP variants.
24 | Layer 3 — Feature Intelligence & Scope Architecture | MEP.24 | Remove-It Test | Challenge founder attachment by testing whether each feature is truly required in the earliest version. | A feature is marked P0/Must Have or scope is still large. | Feature; core loop; outcome; evidence goal; dependencies. | Ask whether the customer can still receive promised value and whether learning still occurs if the feature is absent for the first operating period. | Keep/remove/postpone decision; rationale. | MEP.25–MEP.29 | The remove-it test cannot be used to remove mandatory safety, privacy, compliance or core reliability controls. | P0/Must Have scope survives explicit removal challenge. | Automated counterfactual scope testing.
25 | Layer 3 — Feature Intelligence & Scope Architecture | MEP.25 | Capital-Fitted MVP Scope Builder | Select the smallest commercially meaningful feature set that completes the core loop inside the Stage-3 capital ceiling and realistic timeline. | Features are classified/scored and capital/timeline constraints are known. | Ranked features; dependencies; core loop; capital envelope; founder capacity; effort/cost ranges. | Walk the ranked list, preserve mandatory controls, stop when the safe envelope is reached, and propose further reduction when required. | Approved/proposed MVP feature set; capital-fit status; reduction recommendation. | MEP.26–MEP.29, MEP.63–MEP.64 | Default posture is reduction, not addition. Preferred scope is the smallest set that completes one useful core loop; counts such as 3–7 or top-5 summaries are heuristics, not universal hard limits. | MVP scope is minimal, traceable, useful and fits capital/time constraints. | Multi-option scope scenarios by budget envelope.
26 | Layer 3 — Feature Intelligence & Scope Architecture | MEP.26 | In-Scope / Out-of-Scope / Future / Non-Goals Architecture | Make Version 1 boundaries explicit so execution teams know exactly what is and is not being attempted. | MVP scope is proposed. | Included features; deferred features; non-goals; geographies; channels; user segments; service boundaries. | Structure four scope zones and attach reasons for exclusions/non-goals. | Scope boundary register. | MEP.27–MEP.29, MEP.49, MEP.82 | Out-of-scope must be explicit; non-goals describe what the MVP deliberately does not optimize or solve. | A builder can identify Version-1 boundaries without interpretation. | Visual scope maps linked to roadmap versions.
27 | Layer 3 — Feature Intelligence & Scope Architecture | MEP.27 | Deferred Feature Trigger & Phase-2 Roadmap | Preserve valuable postponed work without allowing it to contaminate MVP scope. | Should/Could/P1/P2 features are deferred. | Deferred features; reason not now; evidence thresholds; customer/usage/economic signals. | Define objective revisit triggers and organize eligible items into a post-MVP/Phase-2 roadmap. | Deferred-feature register; revisit triggers; Phase-2 roadmap. | MEP.28, MEP.82, Stage 7/9 agents | Do not label work merely 'Phase 2'; every postponed feature needs a trigger tied to evidence, volume, segment, support burden or economics. | Deferred work has a clear reason and measurable condition for reconsideration. | Automated trigger detection from downstream traction data.
28 | Layer 3 — Feature Intelligence & Scope Architecture | MEP.28 | Scale-Phase Roadmap | Keep long-term scale ambitions visible while preventing them from consuming MVP capital or timeline. | Scale-only features are identified. | P3/scale features; later-stage lifecycle triggers; automation/platform expansion ideas. | Record scale features and bind them to later-stage evidence gates such as traction, break-even, volume or enterprise demand. | Scale-phase feature roadmap with explicit gates. | Stage 9/10 agents; Axiora Prism; MEP.79 | Scale features are informational in Stage 4; do not budget or schedule them as current MVP work. | Long-term scale items remain visible without distorting current execution. | Cross-stage roadmap visualization.
29 | Layer 3 — Feature Intelligence & Scope Architecture | MEP.29 | Scope Freeze & Change Control | Prevent mid-cycle scope creep and preserve capital/timeline discipline after approval. | MVP scope is approved or a new request arrives after lock. | Current scope version; new request; value/effort/dependency/cost/timeline impact; decision owner. | Log request, assess impact, require formal reprioritisation and identify equivalent trade-off/release impact. | Scope-change record; approve/defer/reject decision; updated version. | MEP.72–MEP.73, MEP.88 | No new feature enters active execution silently. Added work must show impact and may require equivalent removal or envelope change. | Every post-lock scope change is versioned, justified and reflected in downstream plan. | Approval workflow integrations.

## Feasibility Delivery Mode
Seq | Layer | Capability ID | Capability Name | Purpose | Trigger | Inputs | Processing | Outputs | Consumed By | Business Rules | Success Criteria | Future Scope
30 | Layer 4 — Feasibility, Delivery Mode & Technical Direction | MEP.30 | Technical Feasibility Assessment | Assess whether the core MVP can be built with available/obtainable technology without pretending to perform final architecture sign-off. | Capital-fitted scope exists or a core technical assumption is raised. | Feature requirements; platforms; APIs; data; performance; hardware; model needs; available skills. | Assess complexity, novelty, feasibility confidence, dependency risks and need for a POC/technical owner. | Technical feasibility rating; red flags; POC/expert-review recommendation. | MEP.32–MEP.38, MEP.75, MEP.79 | Stage 4 guidance is directional. Final architecture and production DevOps decisions remain with qualified technical owners. | Core build path is credible or clearly blocked/conditional. | Architecture-review connector for Stage 5.
31 | Layer 4 — Feasibility, Delivery Mode & Technical Direction | MEP.31 | Operational Feasibility Assessment | Confirm the MVP can actually be delivered, fulfilled and supported at the intended first-user volume. | MVP scope includes service, fulfilment, physical operations or manual components. | Delivery process; locations; suppliers; staffing; turnaround; capacity; support/refund/exception paths; founder dependency. | Assess workflow practicality, support burden, capacity, failure handling and operational bottlenecks. | Operational feasibility rating; operating constraints; fallback requirements. | MEP.38–MEP.52, MEP.74 | A technically working product is not viable if fulfilment/support cannot deliver the promised outcome at minimum quality. | Operational path can support the first users with known exception handling. | Capacity simulation by demand level.
32 | Layer 4 — Feasibility, Delivery Mode & Technical Direction | MEP.32 | Architecture, Third-Party & Dependency Risk Scan | Identify single points of failure and avoid unnecessary scale/complexity before build. | Technical/operational feasibility assessment. | External APIs/vendors; cloud/services; suppliers; payment gateways; integration contracts; scale assumptions; support dependencies. | Assess availability, lock-in, pricing-change, SLA, fallback, access, documentation and over-engineering risks. | Architecture/dependency risk register; fallback needs; no-go flags. | MEP.35–MEP.38, MEP.68–MEP.75 | Do not over-engineer for scale not yet needed; any critical dependency needs a documented fallback or explicit risk acceptance. | No hidden single point of failure exists for the core loop. | Automated provider-risk monitoring.
33 | Layer 4 — Feasibility, Delivery Mode & Technical Direction | MEP.33 | Data, AI & Integration Feasibility | Validate that required data, AI behavior and integrations are realistically available, lawful and reliable enough for MVP. | MVP relies on data, AI/model inference or system integrations. | Data sources/rights; API access; quality; latency; accuracy; hallucination/fallback expectations; integration permissions and effort. | Assess availability, legality, reliability, error/fallback behavior and whether uncertain AI/integration elements require POC first. | Data/AI/integration feasibility status; constraints; POC/fallback recommendation. | MEP.34–MEP.38, MEP.45–MEP.52, MEP.75 | Never assume unavailable data or perfect AI performance. Critical uncertain AI/integration behavior must be proven before expensive build. | Core AI/data/integration dependencies have credible evidence, controls and fallback paths. | Model/provider benchmarking once governed evidence exists.
34 | Layer 4 — Feasibility, Delivery Mode & Technical Direction | MEP.34 | Quality, Security, Privacy & Compliance Feasibility Gate | Protect customer trust by ensuring minimum quality and mandatory controls are feasible within the reduced scope. | Scope reduction or delivery approach could affect trust/safety/compliance. | Core outcome; sensitive data; auth/access needs; regulated-domain exposure; reliability requirements; customer expectations. | Check feasibility of required usability, reliability, security, privacy, consent, compliance and operational support standards. | Minimum-quality feasibility status; mandatory controls; expert-review flags. | MEP.45–MEP.52, MEP.75, MEP.79 | Reduce scope, not trust. Security/privacy/compliance/core quality are not optional shortcuts to ship faster. | Every P0/Must Have can meet minimum trust and mandatory requirements before execution. | Domain-specific control packs.
35 | Layer 4 — Feasibility, Delivery Mode & Technical Direction | MEP.35 | Delivery Mode Decision — Build / Buy / Integrate / Outsource / Manual | Choose the most capital-efficient delivery mode per capability rather than defaulting to custom development. | A feature/capability has a known requirement and feasibility profile. | Differentiation; available tools/providers; lock-in; compliance; cost/time; manual feasibility; control/knowledge needs; founder experience; risk appetite; maximum acceptable loss. | Compare build, buy/configure, integrate, outsource, manual/concierge and white-label options; select the lowest-risk, most reversible option that preserves required value/control and stays inside the founder's governed risk/capital boundary. | Per-capability delivery-mode decision with rationale, reversibility and risks. | MEP.36–MEP.37, MEP.55–MEP.63 | Commodity capabilities should not become custom builds without justification. Core IP/control may justify build; unsafe/unmanageable manual delivery is rejected. Risk appetite cannot override protected reserves, compliance, quality or hard gates. | Each material capability has a justified delivery mode linked to evidence needs, reversibility, capital and founder risk boundary. | Provider recommendation marketplace.
36 | Layer 4 — Feasibility, Delivery Mode & Technical Direction | MEP.36 | Directional Technology Stack & Platform Guidance | Translate MVP requirements into non-prescriptive technology/platform categories suitable for current scale and budget. | Technology direction is needed after delivery-mode analysis. | Platform/device needs; target customer behavior; technical requirements; founder skills; integration/security needs; budget/timeline. | Recommend direction such as WhatsApp-first, responsive web, native mobile only when structurally required, managed services, no-code/low-code or standard web stack categories. | Directional stack/platform recommendation; trade-offs and cautions. | MEP.37, MEP.49, Stage 5 technical owner | Do not lock a founder into specific vendors or present a final architecture. Single-platform MVP is preferred unless the model structurally requires more. | Technical owner receives usable direction without mistaking it for final architecture approval. | Governed vendor/catalog recommendations.
37 | Layer 4 — Feasibility, Delivery Mode & Technical Direction | MEP.37 | Development Approach Recommendation | Recommend the overall build-resource approach appropriate to scope, founder capability and capital. | MVP scope and technology direction are known. | Founder skills/experience/capacity; founder risk appetite; maximum acceptable loss; capital/runway; spec clarity; required disciplines; timeline; quality needs. | Compare in-house, freelancer(s), agency, technical co-founder and no-code/self-build options across fixed cost, reversibility, pivotability, oversight, capability fit and downside exposure. | Preferred development approach; alternatives; downside/risk rationale. | MEP.55–MEP.63 | Stage 4 recommends an approach; it does not hire, contract or make binding staffing decisions. A higher founder risk appetite does not justify survival-runway exposure or ungoverned fixed-cost commitments. | Recommended approach fits scope, founder oversight/experience, acceptable-loss boundary and Stage-3 capital posture. | Historical vendor/team performance evidence.
38 | Layer 4 — Feasibility, Delivery Mode & Technical Direction | MEP.38 | Industry & Business-Type Adaptation Playbooks | Adapt first-bet, scope, feasibility, evidence and delivery recommendations to the business model. | Business type/industry is classified. | SaaS/AI; F&B; D2C/retail; service; marketplace; manufacturing/physical product; education; B2B enterprise; existing-business expansion. | Apply domain-specific patterns such as single workflow, cloud kitchen/pop-up, hero SKU, packaged service, manual seeding, sample batch, single cohort or controlled enterprise pilot. | Industry-adapted MVP pattern; domain risks; evidence targets. | All Stage 4 capabilities | Industry adaptation changes the pattern and evidence needs, not core capital-safety, quality or explainability principles. | Different industries receive domain-appropriate first-bet and evidence recommendations rather than a SaaS-only template. | Additional regulated and international industry packs.

## Requirements UX and Quality
Seq | Layer | Capability ID | Capability Name | Purpose | Trigger | Inputs | Processing | Outputs | Consumed By | Business Rules | Success Criteria | Future Scope
39 | Layer 5 — Requirements, UX & Quality Specification | MEP.39 | MVP Journey / Service Blueprint | Define the end-to-end customer/service journey that the MVP must support. | Scope and delivery model are stable enough for requirements. | Primary customer; core loop; in-scope capabilities; service/operations model. | Map entry, onboarding/setup, activation, core task, value moment, completion/result, return/repeat and feedback/support points. | MVP user journey/service blueprint. | MEP.40–MEP.52, MEP.76 | Journey must show where value is realized and where evidence is captured; do not optimize unrelated peripheral journeys. | All P0 capabilities fit into one coherent end-to-end journey. | Journey variants by persona after MVP.
40 | Layer 5 — Requirements, UX & Quality Specification | MEP.40 | Requirement Decomposition & Capability Specification | Convert approved scope into buildable functional/service requirements without dictating final technical architecture. | MVP scope and journey are approved. | In-scope features; journey; business context; delivery mode; feasibility constraints. | Decompose features into requirement statements, inputs/outputs, dependencies, validations and service/process needs. | PRD-ready requirement set; capability decomposition. | MEP.41–MEP.52, MEP.59, MEP.64 | Requirements define what/why and constraints; qualified technical owners decide implementation architecture. | Every P0 item has enough detail to estimate, design and test. | Automatic backlog/story decomposition.
41 | Layer 5 — Requirements, UX & Quality Specification | MEP.41 | User Story Generation | Express user-facing requirements in a consistent persona-action-outcome format. | A functional requirement involves a user or operator action. | Specific user/role; requirement; core outcome; journey context. | Generate user stories linked to requirements and traceability IDs. | User-story set. | MEP.42, MEP.49, MEP.66 | Stories must reference a specific user and measurable value; avoid generic 'as a user' where role matters. | User stories trace cleanly to MVP requirements and outcomes. | Team-tool export formats.
42 | Layer 5 — Requirements, UX & Quality Specification | MEP.42 | Acceptance Criteria & Definition of Done | Make 'done' objective before build starts and protect against demo-only or incomplete delivery. | P0/Must Have and applicable P1/Should Have requirements are defined. | User stories; business rules; happy path; validation; errors; data; permissions; quality; analytics; privacy/security requirements. | Create testable acceptance criteria covering end-to-end completion and a Definition of Done including testing, UX states, analytics, risks and required controls. | Acceptance criteria; feature-level DoD. | MEP.49, MEP.52, MEP.65, Stage 5 QA/UAT | Every Must Have requires acceptance criteria before Stage 4 exit; testing must include someone other than the builder where applicable. | All P0 acceptance criteria are objective and independently testable. | Executable acceptance-test generation.
43 | Layer 5 — Requirements, UX & Quality Specification | MEP.43 | Functional Rules, Validation & Permission Specification | Define the business logic that keeps the MVP in valid, authorized states. | Requirement decomposition identifies rules or role restrictions. | Data fields; user roles; process states; pricing/delivery logic; exceptions. | Specify validation rules, state transitions, permissions, required/optional fields and operational rules. | Business-rule catalogue; validation/permission rules. | MEP.42, MEP.49, MEP.52 | Rules must preserve upstream business model and compliance constraints; contradictions are escalated rather than silently changed. | Builders and testers can determine valid/invalid behavior unambiguously. | Rules-engine export.
44 | Layer 5 — Requirements, UX & Quality Specification | MEP.44 | AI Capability Input → Behaviour → Output Specification | Make any AI-dependent MVP behavior explicit and testable. | An in-scope capability uses AI/ML/LLM reasoning. | User/system inputs; model/data sources; intended behavior; output format; accuracy/latency/fallback requirements; risk controls. | Define input contract, model behavior, confidence/explainability, fallback, prohibited behavior and expected output. | AI I→B→O specification; model-risk acceptance criteria. | MEP.42, MEP.49, Stage 5 AI/ML team | Do not imply guaranteed accuracy; unsafe or uncertain AI behavior requires fallback and/or POC evidence. | AI behavior is specific enough to evaluate and implement safely. | Model evaluation suites linked to production telemetry.
45 | Layer 5 — Requirements, UX & Quality Specification | MEP.45 | Data & Integration Requirement Specification | Define the minimum data, API, storage, file/media and integration requirements needed for the core loop. | MVP uses persistent data, external systems or files/media. | Data entities; sources; API/provider needs; import/export; payments; notifications; file/media flows; retention needs. | Specify required data fields, integration contracts, availability assumptions, access prerequisites and failure handling. | Data/integration requirement package. | MEP.49, MEP.52, MEP.68, Stage 5 technical implementation | Only core-loop data/integrations belong in MVP; unavailable permissions/access are explicit dependencies. | All required data/integration assumptions are visible before build. | Schema/API contract generation.
46 | Layer 5 — Requirements, UX & Quality Specification | MEP.46 | Security, Privacy & Compliance Requirement Specification | Translate trust/regulatory exposure into concrete MVP requirements and escalation points. | Sensitive data, authentication, payments or regulated-domain exposure exists. | Data categories; roles; access; consent; retention/deletion; encryption need; anonymization; applicable sector requirements. | Specify auth/access control, data minimization, consent, deletion/retention, sensitive-data handling, anonymization and mandatory review needs. | Security/privacy/compliance requirements; professional-review flags. | MEP.49, MEP.52, MEP.90 | Regulated legal conclusions are not produced by the agent. Relevant matters must be reviewed by qualified professionals before irreversible build. | Required controls are identified before development, not discovered after build. | Jurisdiction-aware compliance rule packs.
47 | Layer 5 — Requirements, UX & Quality Specification | MEP.47 | Error Handling & Edge-Case Specification | Ensure critical failure paths are understandable and recoverable rather than leaving only a happy-path MVP. | Requirements and integrations are being finalized. | Invalid inputs; dependency failure; unavailable data; permissions; timeouts; refund/exception cases; conflicting states. | Enumerate material edge cases and define recoverable user/operational behavior and escalation. | Error/edge-case catalogue; recovery behavior. | MEP.42, MEP.49, MEP.52, Stage 5 QA | Core-path failures must fail gracefully; no silent errors or dead ends. | Critical error and exception paths are specified before build. | Failure-mode library by integration type.
48 | Layer 5 — Requirements, UX & Quality Specification | MEP.48 | Analytics, Telemetry & Evidence Event Specification | Instrument the MVP so it can answer the evidence questions defined by Stage 4. | Core loop and measurement plan are defined. | Journey steps; evidence goals; adoption/activation/completion/outcome/payment/repeat/support metrics. | Identify critical events, properties, data sources and feedback capture points required to evaluate the MVP. | Analytics event map; evidence-event requirements. | MEP.49, MEP.76, MEP.81, Stage 5 implementation | No vanity metrics. Instrument only events needed for decisions, customer value and quality/risk monitoring. | Measurement events are defined before development so evidence is not added after the fact. | Automated event-taxonomy validation.
49 | Layer 5 — Requirements, UX & Quality Specification | MEP.49 | PRD Assembly & Requirement Traceability | Create the single Stage 4 source of truth for development handover. | Core requirements, rules, scope and quality criteria are available. | Problem/customer/outcome; thesis; scope; journey; features; stories; AC; business rules; AI behavior; data/integration; security/privacy; edge cases; dependencies; analytics; release criteria. | Assemble a versioned PRD-ready package and maintain traceability from source evidence to requirement to test/evidence. | PRD-ready specification; traceability matrix. | MEP.50–MEP.73, MEP.84 | PRD is planning/specification output, not final technical architecture or a signed vendor contract. | Stage 5 receives one coherent, versioned source of truth. | Direct delivery-tool synchronization.
50 | Layer 5 — Requirements, UX & Quality Specification | MEP.50 | Design Handover Package | Define the design work required to make the MVP usable and testable without over-investing in polish. | PRD-ready scope is stable enough for design. | Journey; features; target device/platform; brand constraints; error/empty/loading states; accessibility needs. | Specify information architecture, flows, wireframes/mockups, prototype needs, responsive/mobile behavior, accessibility basics and design decision log. | Design handover checklist/package. | MEP.51–MEP.52, Stage 5 design team | Brand-consistent credibility is required, but custom visual systems/polish that do not affect proof are deferred. | All P0 states and key UX flows can be designed without unresolved scope ambiguity. | Design-system component mapping.
51 | Layer 5 — Requirements, UX & Quality Specification | MEP.51 | MVP UX Quality Principles | Protect early-user completion by minimizing friction while preserving trust and required controls. | Journey/design decisions are made. | Target device behavior; onboarding steps; KYC/setup needs; core task; UX dependencies. | Apply core-loop-first, simplicity, minimal onboarding, mobile-first where appropriate, and fit-for-purpose polish principles. | UX quality requirements; friction-reduction recommendations. | MEP.52, MEP.76 | Do not remove mandatory KYC/security/compliance to reduce friction; do not add decorative steps that dilute evidence. | Target users can reach core value with acceptable friction on the primary platform. | Accessibility-depth expansion for later phases.
52 | Layer 5 — Requirements, UX & Quality Specification | MEP.52 | Release / Pilot-Readiness Criteria | Define the minimum condition under which Stage 5 can prepare a controlled release/pilot. | Requirements, acceptance criteria and quality controls are defined. | Acceptance criteria; test results requirements; UX states; error handling; analytics; risk register; security/privacy controls; business-owner validation. | Create release gate covering functional completion, trust/quality, operability, measurement and unresolved critical risks. | Pilot/release-readiness checklist and gate. | MEP.76–MEP.86, Stage 5/7 | A smaller MVP can ship with fewer capabilities, but not with broken core workflow, unprotected data or unresolved mandatory blockers. | Controlled release criteria are objective and tied to customer value and evidence. | Automated readiness evidence aggregation.

## Resource, Cost and Capital Fit
Seq | Layer | Capability ID | Capability Name | Purpose | Trigger | Inputs | Processing | Outputs | Consumed By | Business Rules | Success Criteria | Future Scope
53 | Layer 6 — Resource, Cost & Capital-Fit Planning | MEP.53 | Resource Capability Map | Identify the capabilities needed to execute the MVP without prematurely converting them into hiring decisions. | PRD/feasibility/delivery approach are sufficiently defined. | Scope; technical/operational requirements; design/QA/security/operations/support/sales/domain needs. | Map required capabilities across product/BA, UX, engineering, AI/data, architecture/cloud, QA, security/privacy, operations, support and domain expertise. | Required capability map; capability gaps. | MEP.54–MEP.58, MEP.84 | Stage 4 identifies capability needs; Stage 5 decides actual staffing/contracting and JDs. | All capabilities necessary for execution/testing are visible before handoff. | Skills graph and internal talent matching.
54 | Layer 6 — Resource, Cost & Capital-Fit Planning | MEP.54 | Resource Criticality & Engagement Classification | Classify when and how each required capability is needed. | Resource capability map exists. | Capability; workload; timing; dependency; business criticality; duration. | Classify as Critical Now, Shared/Part-Time, Specialist, Future Hire or Scale role and identify timing. | Resource classification; timing plan. | MEP.55–MEP.58, MEP.84 | Do not imply full-time employment when the need is bounded or intermittent. | Resource plan distinguishes immediate critical gaps from later staffing. | Capacity-demand curves.
55 | Layer 6 — Resource, Cost & Capital-Fit Planning | MEP.55 | Lean Resource Ladder | Minimize fixed commitments by exhausting lower-cost, fit-for-stage resourcing options first. | A capability gap needs to be filled. | Founder skill; existing team; tools/no-code; part-time/freelance/specialist/vendor options; scope and quality needs. | Evaluate founder → existing team → tool/no-code → part-time/shared → freelancer/specialist → agency/vendor → full-time only if justified. | Lean resourcing recommendation per capability. | MEP.56–MEP.58, MEP.84 | Founder/self-delivery is accepted only when safe/effective; fixed hiring is not the default at the riskiest stage. | Recommended resource model minimizes fixed cost without sacrificing required capability/quality. | Marketplace sourcing options.
56 | Layer 6 — Resource, Cost & Capital-Fit Planning | MEP.56 | Build-Resource Readiness | Determine whether at least one credible execution resource/path exists before Stage 4 exit. | Development approach and capability needs are known. | Founder/self-build capability; freelancer/agency/cofounder candidates; technical owner availability; critical skill gaps. | Assess whether a named/viable resource path exists for all critical capabilities. | Resource-readiness status; unresolved gaps; Stage-5 prerequisite. | MEP.57–MEP.63, MEP.79, MEP.84 | No Stage-5 progression when no credible build resource/path exists for critical work. | Critical execution ownership is identified or explicitly conditional before handoff. | Verified-resource directory.
57 | Layer 6 — Resource, Cost & Capital-Fit Planning | MEP.57 | Vendor / Freelancer / Agency Evaluation | Provide a structured pre-contract evaluation so founders can compare external build options on more than price. | Founder considers external delivery resources. | Portfolio; proposal; pricing; milestones; communication; handover terms; timeline; references; scope fit. | Evaluate relevant experience, communication, milestone pricing, source/credential/documentation handover and timeline realism. | Vendor evaluation scorecard; red flags; comparison. | MEP.58, MEP.84 | Stage 4 does not sign contracts or guarantee vendor performance; suspiciously fast timelines or full upfront payment are red flags. | Founder can compare candidates using consistent evidence and safeguard criteria. | Verified reference/reputation signals.
58 | Layer 6 — Resource, Cost & Capital-Fit Planning | MEP.58 | Vendor Milestone, Acceptance & Handover Safeguards | Translate scope/DoD into capital-protective vendor terms for Stage-5 review. | External delivery is likely. | Milestones; acceptance criteria; source/code/assets; credentials; documentation; payment schedule. | Define recommended milestone-based payment/acceptance structure and required handover items. | Vendor safeguard checklist; milestone/acceptance plan. | MEP.63, MEP.84 | Any contract language is draft planning guidance and requires founder/legal review; no recommendation should normalize full upfront payment without safeguards. | Stage 5 receives clear non-binding acceptance/handover requirements. | Contract-template integration under legal review.
59 | Layer 6 — Resource, Cost & Capital-Fit Planning | MEP.59 | Effort Sizing & Work Decomposition | Estimate relative effort without false precision and identify work too large for one executable item. | Requirements are stable enough for sizing. | Feature/work-package complexity; dependencies; unknowns; resource approach. | Assign relative size (e.g., XS/S/M/L/X), decompose X/large items, and flag uncertainty. | Effort profile; decomposed work items; estimation confidence. | MEP.60–MEP.73 | Estimates are directional until confirmed by actual technical/resource quotes; sizing exists to expose disproportionate effort/risk. | No active work package is too large/ambiguous to plan credibly. | Historical estimation calibration.
60 | Layer 6 — Resource, Cost & Capital-Fit Planning | MEP.60 | Directional MVP Cost Estimation | Estimate the cost envelope by category so the founder can compare plans before committing capital. | Scope, effort and build approach are known. | Design; development; infrastructure; testing/QA; launch essentials; operations/physical costs where relevant; quoted/range evidence. | Build category-level directional ranges tied to scope/complexity and mark unknowns. | Directional MVP cost range; cost breakdown; confidence. | MEP.61–MEP.63, MEP.81 | Never fabricate precise cost. Real quotes/provider pricing must replace placeholders before capital commitment. | Founder sees an evidence-labelled cost range that can be tested against Stage-3 capital. | Market-rate benchmark connectors.
61 | Layer 6 — Resource, Cost & Capital-Fit Planning | MEP.61 | Quote Validation & Estimate Confidence | Reconcile real quotes or benchmark evidence with directional estimates and update scope/capital fit. | A vendor/tool/supplier quote arrives or cost assumptions change. | Directional estimate; external quotes; provider pricing; scope version; source/date. | Validate scope equivalence, identify excluded items, compare ranges, update confidence and flag material variance. | Validated quote comparison; revised cost range; variance alert. | MEP.62–MEP.63, MEP.73, MEP.88 | Quotes are not comparable if scope/acceptance/handover differs; material overruns trigger re-scope before approval. | Cost fit reflects current comparable evidence rather than stale placeholders. | Quote-normalization automation.
62 | Layer 6 — Resource, Cost & Capital-Fit Planning | MEP.62 | Cost Optimisation & Reversible Alternative Analysis | Reduce spend without cutting core value or trust by identifying lower-cost ways to prove the same outcome. | Cost/effort is high or capital fit is tight. | Cost categories; delivery modes; scope; volume/geography; tool/rental/usage-based/manual alternatives; paid-pilot/pre-sale possibility. | Test whether costs can be reduced, rented, outsourced, usage-based, simplified, volume-limited or partly funded by early customers. | Cost-reduction options; savings/risk trade-offs. | MEP.63, MEP.73 | Spend to prove, not to look established. Do not trade away mandatory quality/security/compliance for savings. | The chosen plan minimizes avoidable spend while preserving evidence and customer outcome. | Automated alternative provider/approach scenarios.
63 | Layer 6 — Resource, Cost & Capital-Fit Planning | MEP.63 | Stage-3 Capital Fit & Capital-Release Gate Plan | Enforce the approved financial envelope and tie planned spend to evidence/milestones. | Cost estimate and execution plan are available or materially updated. | Adjusted planning-capital figure; protected reserves; maximum acceptable loss; MVP budget; cost range; milestones; evidence gates; quotes. | Compare plan against the Stage-3 safe deployable ceiling and acceptable-loss boundary; block protected-reserve use; define release gates from proof/scope/core loop/quality/evidence milestones; rerun scope cuts when breached. | Capital-fit status; acceptable-loss check; gated spend plan; hard-stop/re-scope requirement. | MEP.64–MEP.86, Stage 3 | Stage 4 enforces but does not redefine capital policy. External funding/loan decisions return to Stage 3. Founder risk appetite or willingness to lose more cannot override protected survival/runway constraints. | No execution plan exceeds the approved safe envelope or acceptable-loss boundary, and spend is tied to proof/evidence milestones. | Live Stage-3 budget synchronization.

## Roadmap, Dependency and Executi
Seq | Layer | Capability ID | Capability Name | Purpose | Trigger | Inputs | Processing | Outputs | Consumed By | Business Rules | Success Criteria | Future Scope
64 | Layer 7 — Roadmap, Dependency & Execution Governance | MEP.64 | Execution Phase Roadmap | Translate approved MVP scope into a phased path from specification through pilot readiness. | Scope, resource and capital fit are sufficiently stable. | Scope; build approach; dependencies; quality gates; founder capacity; evidence needs. | Sequence discovery/spec finalisation, POC/prototype, design, build/service setup, integration, internal validation, QA/UAT preparation, pilot readiness and support/documentation. | Phase-based execution roadmap. | MEP.65–MEP.73, MEP.81, MEP.84 | Roadmap represents planned outcomes, not a promise of universal 4–8 week completion. | Roadmap covers all required execution preparation without unsupported dates. | Scenario roadmaps by alternative build approach.
65 | Layer 7 — Roadmap, Dependency & Execution Governance | MEP.65 | Milestone Outcome Definition | Replace vague percentage-complete milestones with observable business/technical outcomes. | Execution phases are defined. | Phase deliverables; core loop; acceptance criteria; evidence gates. | Define each milestone as a demonstrable outcome and attach acceptance/evidence conditions. | Outcome-based milestone set. | MEP.66–MEP.73, MEP.79 | Avoid milestones such as 'development 50%'; use end-to-end workflow/value/quality outcomes. | Every milestone can be objectively reviewed as passed/not passed. | Milestone templates by business type.
66 | Layer 7 — Roadmap, Dependency & Execution Governance | MEP.66 | Sprint / Work-Package Planning | Break the roadmap into bounded units of committed work appropriate to the business and build model. | Milestones and scope are approved. | Prioritized features; owners/capabilities; dependencies; effort; founder capacity; acceptance criteria. | Create sprints or work packages with goal, scope, owner capability, DoD, dependencies, risks and demo/evidence event. | Sprint/work-package plan. | MEP.67–MEP.73, MEP.84 | Use sprints where appropriate; physical/service businesses may use work packages rather than software cadence. | Each execution unit has one visible goal, owner and acceptance/evidence condition. | Tool-specific backlog export.
67 | Layer 7 — Roadmap, Dependency & Execution Governance | MEP.67 | Task Ownership & Lightweight RACI | Make responsibility and decision authority explicit for a solo founder or small team. | Work packages and decisions are defined. | Tasks/decisions; founder; build resource; QA/support; Stage-3 guidance; consulted specialists. | Assign responsible/accountable/consulted roles and distinguish scope decisions, build execution, acceptance and budget-release guidance. | Ownership/RACI matrix. | MEP.72, MEP.84 | Founder remains accountable for product/scope decisions; external resources own execution only within agreed scope. Stage 4 does not assume execution authority. | No critical task or decision lacks an accountable owner. | Role-based notifications.
68 | Layer 7 — Roadmap, Dependency & Execution Governance | MEP.68 | Dependency Register | Expose prerequisites and blockers before they create hidden schedule/cost risk. | Roadmap/work packages are built. | Internal design/build dependencies; APIs/vendors; regulatory approvals; resources; customer/pilot access; data/integration permissions. | Capture dependency type, owner, due date/condition, impact, status and required fallback. | Dependency register; blocker list. | MEP.69–MEP.73, MEP.74 | Mandatory regulatory/data/access dependencies cannot be assumed away. | All critical-path prerequisites are visible with owners and conditions. | External dependency status integrations.
69 | Layer 7 — Roadmap, Dependency & Execution Governance | MEP.69 | Critical Path & Dependency Fallback Planning | Identify the smallest set of activities controlling the earliest credible MVP/pilot-ready date and prepare fallbacks. | Dependencies and work packages exist. | Dependency graph; durations/ranges; external availability; fallback options. | Identify critical path/near-critical dependencies and define reduced-scope, alternative-provider, manual or sequencing fallback where possible. | Critical path; earliest credible date range; fallback plan. | MEP.70–MEP.73, MEP.75 | Deadline claims must reflect the critical path, not founder preference; no fallback is invented where none exists. | Schedule risk is concentrated on visible dependencies with contingency actions. | Monte Carlo schedule-risk estimation.
70 | Layer 7 — Roadmap, Dependency & Execution Governance | MEP.70 | Timeline Realism & Founder-Capacity Fit | Set credible timeline bands and challenge impossible deadlines using actual scope, dependencies and founder capacity. | Timeline/deadline is proposed or changes. | Work packages; critical path; founder mode; build approach; external deadlines; compliance/supplier lead times. | Estimate directional timeline, compare to deadline and show what must be reduced/resequenced if the target is not credible. | Timeline range; at-risk/slipping status; reduction/replan options. | MEP.72–MEP.73, MEP.78–MEP.79 | No universal 4–8 week promise. If a deadline is unrealistic, show the critical path and trade-offs instead of claiming certainty. | Timeline is explainable from scope/capacity/dependencies and external constraints. | Historical cycle-time calibration.
71 | Layer 7 — Roadmap, Dependency & Execution Governance | MEP.71 | Recommended Operating Rhythm | Give the founder a lightweight cadence for keeping the plan moving without Stage 4 becoming day-to-day project management. | Execution plan is being prepared for handoff. | Build approach; founder capacity; sprint/work-package structure; QA needs. | Recommend kickoff, short stand-ups/check-ins, product/leadership sync, review/demo, backlog grooming and parallel QA preparation as appropriate. | Suggested operating cadence. | MEP.72, MEP.84 | Cadence is guidance only; Pulse does not manage a live team or automate operational delivery. | Founder has a practical review rhythm aligned to the chosen execution mode. | Calendar/task connector integration.
72 | Layer 7 — Roadmap, Dependency & Execution Governance | MEP.72 | Roadmap & Execution Tracker | Provide founder-updated visibility of planned milestones/tasks without taking control of execution. | Stage 4 roadmap exists and founder reports progress/status. | Roadmap; owners; target dates; task status; dependencies; capital gates. | Track status, blocked/slipping items, completed outcomes and current next decision. | Execution status view; tracker updates; blocked-item list. | MEP.73, MEP.81, MEP.83 | Tracker is planning/visibility, not live team management or automation; status relies on founder/team updates unless later integrations are explicitly enabled. | Founder can see what is on track, blocked and next without confusing Pulse with a PMO. | Optional external task-system sync.
73 | Layer 7 — Roadmap, Dependency & Execution Governance | MEP.73 | Slippage, Scope-Impact & Replan | Respond to schedule, scope, vendor or cost drift with explicit replanning rather than silent timeline movement. | A milestone/task slips materially, a dependency fails or scope/cost changes. | Current plan; status variance; cause; capital impact; dependency changes; scope version. | Diagnose likely cause, assess scope/capital/evidence impact, recompute affected downstream items only and propose re-sequencing/reduction/fallback. | Replan recommendation; affected plan version; new blockers/actions. | MEP.75–MEP.83, MEP.88 | Do not silently extend dates. Material change requires explicit impact visibility and version update. | Plan changes remain traceable and protect capital/evidence goals. | Automated dependency-aware replanning suggestions.

## Risk, Evidence, Readiness, Hand
Seq | Layer | Capability ID | Capability Name | Purpose | Trigger | Inputs | Processing | Outputs | Consumed By | Business Rules | Success Criteria | Future Scope
74 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.74 | MVP Risk Register & Founder Mistake Prevention | Maintain execution risks and proactively surface common founder behaviors that create avoidable cost, delay or fragility. | Scope/plan is created or material risk changes. | Scope; technical/vendor/resource/cost/timeline/security/regulatory/customer-access risks; founder decisions. | Record probability, impact, early warning, prevention, contingency and owner; flag patterns such as full-dream build, premature hiring, automation-before-proof, prestige tech and weak acceptance/payment safeguards. | Risk register; founder-mistake warnings; mitigations. | MEP.75–MEP.86 | Warnings must be evidence/context-linked, not generic fear. Avoid repeated warnings that add no new decision value. | Critical execution and founder-behavior risks are visible with owners/actions before handoff. | Risk-pattern learning from outcomes.
75 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.75 | Critical Alert & Stop / Hold Logic | Create non-negotiable alerts for conditions that make continued preparation unsafe or irresponsible. | Capital breach, missing resource, scope creep, compliance issue or fatal assumption appears. | Capital fit; build-resource status; scope-change data; regulated-data exposure; quality blockers; evidence conditions. | Classify alert severity and trigger hard stop, hold, reduce scope, POC first, professional review or return-to-validation as required. | Critical alert; blocked decision; required corrective action. | MEP.78–MEP.86 | Examples include cost above capital ceiling, no credible resource, unresolved regulated-data plan, protected reserve use, untested critical technical assumption or uncontrollable scope. | Critical conditions cannot be bypassed by a high readiness score. | Configurable alert policies by business type.
76 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.76 | Measurement & MVP Evidence Plan | Define what real-world evidence the MVP must generate and how it will be interpreted. | MVP thesis/core loop and readiness planning are mature enough. | Evidence goal; journey; analytics events; customer/pilot access; unit delivery cost; support process. | Define adoption, activation, completion, outcome, quality, repeat, payment/commitment, satisfaction/trust, support burden, unit delivery cost and failure/drop-off evidence as applicable. | MVP evidence plan; metric definitions; collection method. | MEP.77–MEP.86, Stage 7 | Metrics are selected for decisions, not vanity. Not every metric applies to every business model. | Evidence plan can determine whether to invest more, redesign, reduce or stop. | Automated downstream evidence ingestion.
77 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.77 | Build Success vs Business Evidence Separation | Prevent 'we built it' from being mistaken for 'the business learned/proved something.' | Milestones or MVP completion are evaluated. | Acceptance results; actual customer behavior; assumption outcomes; commercial evidence. | Separate specification/feature completion from customer-value/business-evidence outcomes and link both to next decisions. | Build-success status; business-evidence status; unlocked/blocked decision. | MEP.78–MEP.80 | Feature acceptance and milestone completion do not by themselves justify further investment. | Every major milestone clearly states both build outcome and business evidence outcome where applicable. | Evidence maturity scoring.
78 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.78 | MVP & Execution Readiness Score | Provide a transparent 100-point readiness assessment of whether the proposed MVP is strategically aligned, customer-outcome focused, disciplined, executable, affordable, safe and capable of generating evidence for the next investment decision. | Sufficient Stage 4 analysis exists to evaluate readiness or any material scope, feasibility, resource, capital, timeline, quality/risk or evidence input changes. | Problem-to-scope alignment; customer outcome; feature discipline; technical/operational feasibility; resource readiness; capital fit; timeline realism; quality/risk; measurement/evidence readiness; source confidence; hard-gate and critical-alert status. | Calculate the approved 9-dimension 100-point model: Problem-to-Scope Alignment 15; Customer Outcome 10; Feature Discipline 15; Technical/Operational Feasibility 10; Resource Readiness 10; Capital Fit 15; Timeline Realism 10; Quality/Risk 10; Measurement/Evidence 5. Show every dimension score and confidence. Apply readiness bands of 85–100 Ready for Execution, 70–84 Ready with Gaps / Proceed with Conditions, 55–69 Reduce/Replan, 40–54 MVP Not Ready, and below 40 Stop Build / return to fundamentals. Then apply hard-gate and critical-alert overrides. | Readiness score; nine dimension scores; readiness band; confidence; gap list; hard-gate/critical-alert override status. | MEP.79–MEP.86 | The 9-dimension Detailed Specification model is the canonical production scoring model. A high numeric score never overrides a failed hard gate, critical alert, capital-ceiling breach, protected-runway exposure, unresolved mandatory compliance/quality blocker, untested fatal technical assumption or missing measurable evidence condition. | The same inputs produce the same dimension and total scores; every score is explainable; readiness gaps map to corrective actions; no blocked plan progresses solely because its numeric total is high. | Outcome-calibrated weighting/threshold refinement only through governed Product/CEO change control after sufficient production evidence.
79 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.79 | Decision Gates & Hard-Gate Override | Evaluate Stage 4 entry/exit conditions that determine whether progression is allowed regardless of score. | Readiness scoring or major Stage 4 decision point. | Prerequisites; feature classification; capital fit; build resource; founder-capacity timeline; AC/DoD; compliance/quality blockers; measurable evidence conditions. | Evaluate gate set and hard blockers, including entry eligibility, scope completeness, capital fit, resource readiness, timeline realism and acceptance completeness. | Gate status; failed gates; progression block/condition. | MEP.80–MEP.86 | Any critical alert/hard-gate failure blocks progression even when numeric score is high. | Progression status is determined by explicit gate logic with no hidden overrides. | Configurable gate sets by delivery type.
80 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.80 | Final Verdict Engine | Turn score, gates and context into an explicit next-step decision. | Readiness score and decision gates are available. | First-bet type; score; hard gates; critical alerts; capital/resource/timeline status; confidence. | Select a normalized verdict such as Proceed/Build MVP, POC First, Prototype First, Manual/Concierge First, Proceed with Conditions, Reduce/Rework Scope, Seek Technical Partner, Replan, Return to Validation or Hold/Pause. | Final verdict; why; biggest risk/opportunity; conditions. | MEP.81–MEP.86, Stage 5 | Verdict language must map equivalent states across the two CEO source taxonomies rather than creating duplicate decision concepts. | Founder receives one unambiguous decision with rationale and conditions. | Decision-history analytics.
81 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.81 | Stage 4 Decision Dashboard | Present readiness as data → insight → decision → action rather than vanity reporting. | Stage 4 analysis exists and is updated. | Score; verdict; confidence; capital fit; feature mix; resource status; timeline; critical path; alerts; next actions. | Render decision-first zones for top verdict, key drivers, scope, execution, risk and next action; show directional/low-confidence states explicitly. | Stage 4 dashboard model/content. | MEP.82–MEP.86, Founder Workspace | Verdict before detail; unsupported estimates must show Directional/Low Confidence rather than precise authority. | User can identify the single biggest blocker and next action from the dashboard. | Interactive what-if scope/capital dashboard.
82 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.82 | Final MVP & Execution Plan Report | Package the Stage 4 analysis into a founder-friendly and execution-team-ready planning document. | Stage 4 reaches reportable state. | Verdict; score; context; gap map; features/scope; feasibility; delivery/resource/cost plan; roadmap; dependencies; risks; acceptance; evidence; handoffs. | Generate a structured report with executive verdict first, followed by context, scope logic, feasibility, execution plan, risk/evidence and handoff detail in simple professional Indian business English. | Axiora Pulse — MVP & Execution Plan Report. | MEP.83–MEP.86, Founder, Stage 5, mentors/leadership | Report is planning guidance, not a signed contract, final engineering specification, legal opinion or guarantee. Recommendations must preserve evidence/confidence labels and end with actionable ownership/next decisions where relevant. | Founder and execution team can act from the same consistent plan without losing rationale, ownership, conditions or source confidence. | Role-specific report views.
83 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.83 | Founder Clarity Summary & Action Roadmap | Close Stage 4 with a one-page founder view of what is being built, what is not, risk, cost fit and immediate actions. | Final verdict/report is prepared. | MVP sentence; Must Haves; exclusions; build approach; cost; capital fit; launch window; biggest risk; verdict. | Summarize current state and produce immediate/7-day/30-day or next-three actions aligned to the current gate. | Founder Clarity Summary; next actions; what must not happen next. | MEP.84–MEP.86, Founder Workspace | Action lists must reflect actual gate failures/risks; do not truncate the real scope merely to satisfy a summary-card display limit. | Founder can state Version 1 and next three actions without reading the full report. | Personalized action nudges.
84 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.84 | Stage 5 — Business Setup & Build Execution Handoff | Transfer an execution-ready requirement and control package without moving Stage 4 into actual hiring/contracting/build execution. | Stage 4 exit conditions are met or conditional handoff is explicitly approved. | Approved scope; core workflows; AC; technical/operational capability requirements; resource classifications; capital gates; roadmap; dependencies; vendor/tool needs; quality/compliance; risks; monitoring expectations. | Create versioned structured handoff and identify unresolved conditions/professional reviews. | Stage-5 Execution Handoff Package. | Business Setup & Build Execution Agent | Actual hiring, vendor contracting, company setup, final architecture approval and live build execution belong to Stage 5/qualified professionals. | Stage 5 receives complete, traceable inputs with no hidden unresolved critical gate. | Automated Stage-5 change-impact notification.
85 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.85 | Stage 6 — Audience Readiness Trigger & Parallel Handoff | Ensure pre-traction/customer preparation starts in parallel with build rather than after product completion. | Stage 5 handoff is being prepared. | Pilot/early customer definition; access channels; problem-led message; waitlist/community/early-access mechanism; evidence requests; MVP timeline. | Define minimum audience-readiness requirements and package them for Stage 6. | Stage-6 customer/audience-readiness handoff. | Pre-Traction & GTM Agent | Stage 4 defines audience-readiness requirements only; it does not execute commercial launch or traction activity. | Stage 6 knows who early customers are, how they will be reached and what proof will be requested. | Coordinated launch-readiness timeline.
86 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.86 | Stage 4 Exit Criteria & Sign-Off | Provide a final completion gate ensuring the plan is genuinely execution-ready. | Founder requests Stage 4 completion or handoff. | Problem; customer; outcome; first-bet; scope; feasibility; capital; resources; timeline; quality; evidence; risk; PRD/AC; handoff packages. | Check all exit conditions/sign-off items and record approval, conditional approval or failure. | Stage 4 sign-off checklist; completion status; unresolved items. | MEP.84–MEP.85 | Stage 4 cannot exit with unresolved hard blockers. Conditional progression must name exact conditions and owners. | All required CEO sign-off checklist areas are complete and traceable. | Digital approval workflow.
87 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.87 | Evidence, Confidence & Explainability Standard | Make every material recommendation auditable and appropriately qualified. | Any major Stage 4 recommendation, estimate or verdict is produced. | Verified data; user-provided inputs; primary evidence; estimates; assumptions; recommendation logic. | Label evidence type, assign High/Medium/Low confidence, and present finding → evidence → risk → recommendation → owner → action/output → expected result → next decision, using simple professional Indian business English. | Evidence/provenance label; confidence; explanation block; owner/action/next-decision block. | All Stage 4 outputs | Strong recommendations cannot be presented from weak inputs without explicit qualification. Cost/time/performance certainty must never be fabricated. Executive verdict/decision comes before detail; material conclusions must end in a clear owner, action/output and next decision. | Material decisions are traceable to evidence, understandable to founders/teams, and actionable without interpretation gaps. | Source-level citations and confidence calibration.
88 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.88 | Cross-Stage Conflict, Versioning & Dependent Recalculation | Handle changed assumptions or contradictions without silently rewriting upstream truth or rerunning unrelated work. | An upstream assumption changes, stakeholder conflict appears or Stage 4 discovers incompatibility with earlier stages. | Current Stage 1–4 versions; changed field; dependent outputs; decision owner; contradiction details. | Surface conflict, identify authoritative decision owner, route affected upstream review where needed, version Stage 4 outputs and rerun only dependent modules. | Conflict record; change-impact map; updated version; upstream review request. | MEP.1, MEP.29, MEP.73, MEP.82, MEP.89 | Do not silently merge incompatible stakeholder requests or alter Stage-1/2/3 conclusions inside Stage 4. | All changed outputs are traceable to the triggering assumption and unaffected modules remain stable. | Graph-based dependency recalculation.
89 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.89 | Structured Output Contract & Data Model | Provide a stable machine-readable Stage 4 schema for UI, analytics and downstream agents. | Stage 4 data is persisted/exported or handed off. | Execution context; MVP thesis; first bet; feature items; scope; feasibility; delivery decisions; resource plan; roadmap; risks; readiness; handoffs. | Validate required fields, IDs, relationships, status values and version metadata across the structured objects. | Structured Stage 4 data package/API contract. | Dashboard, reports, Stage 5, Stage 6, platform analytics | Structured output must preserve scope links, evidence, confidence, hard gates and unresolved professional reviews. | UI and downstream agents can consume Stage 4 outputs without semantic loss. | Formal schema registry and compatibility checks.
90 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.90 | Governance, Authority & Scope-Boundary Guardrails | Keep the Stage 4 agent within planning/decision support and route binding/high-risk decisions to the correct owner. | A request touches contracts, hiring, final architecture, legal/compliance, external capital, live team management, brand/marketing positioning or operational automation. | User request; risk category; stage ownership; professional-review status. | Classify authority, provide non-binding planning guidance where appropriate, escalate professional/technical decisions and redirect live operations to Stage 5/Prism/downstream stages. | Guardrail decision; owner/escalation; stage redirect; disclaimer. | Stage 3/5/6; Axiora Prism; qualified professionals/technical owners | Pulse plans and tracks; it does not code, hire, sign contracts, manage live teams, decide loans/investments, give final legal opinions or approve final technical architecture. Founder-facing brand/positioning language remains draft pending designated owner sign-off. | High-risk/out-of-scope requests are consistently routed without false authority. | Role-aware approval workflows.
91 | Layer 8 — Risk, Evidence, Readiness, Handoff & Governance | MEP.91 | Agent QA, UAT, Training & Regression Governance | Ensure the agent consistently produces smaller, testable, capital-fit, high-quality plans across industries and edge cases. | Agent/prompt/rule/scoring/playbook change or scheduled release review. | Gold test cases; founder narratives; industry scenarios; adversarial scope cases; low-data cases; acceptance criteria; outcome feedback. | Run tests for scope reduction, context consistency, no fabrication, first-bet classification, traceability, capital/hard-gate enforcement, industry adaptation, explainability, escalation and Stage4/5/7 boundaries. | Evaluation report; UAT result; regression issues; release sign-off. | Product/BA/AI/Engineering/QA/Leadership | Release only when the agent reduces avoidable scope without sacrificing core quality and behaves appropriately outside SaaS examples. | Critical regression blocks release and all mandatory UAT scenarios pass. | Outcome-based policy/model improvement under controlled governance.